## Slide 1
2020 ANNUAL STRATEGIC PLANNING SESSION
OMF PHASE II
WORKSTREAM 2

## Slide 2
Presentation outline
1 | Purpose
2 | Legislative framework
3 | Public Service Operations Management Framework
4 | DCS Value Chain
5 | Composition of Work Streams & sub - work streams
6 | Progress Workstream deliverables
7 | Planned deliverables and timeframes
8 | Conclusion

## Slide 3
OMF Phase II (Workstream 2)
Purpose
The purpose of the presentation is to:
Provide context to the DCS Operations Management Framework Phase II with a focus on the deliverables of Workstream 2: People and Technology.
Provide a summary of the guiding prescripts, guidelines, policy mandates that inform the work to be delivered by Workstream 2: People and Technology.
Indicate the core members of Workstream 2: People and Technology that have been appointed to deliver on Phase II.
Provide progress of the work completed by Workstream 2: People and Technology since the appointment of the workstream leaders and members in February 2019 (18 months).
Indicate the outstanding deliverables for Workstream 2: People and Technology with timeframes against the OMF Phase II Charter.
Provide concluding remarks on the deliverables of Workstream 2: People and Technology and the movement into the next phase.
Notes: Not for presentation purposes
This is important background information that will guide managers on what the content is focusing on

## Slide 4
OMF Phase II (Workstream 2)
Legislative framework - Workstream 2
Notes: Not for presentation purposes
This is important background information that will guide managers on what the content is focusing on

## Slide 5
OMF Phase II (Workstream 2)
DCS Operations Management Framework
DCS STRATEGY
OPERATIONS
Transformed Resources
Material
Information
Service Beneficiaries
Transformed Resources
Facilities
Officials
National Development Plan | Medium-Term Strategic Framework | Strategic plan | Annual Operational Plan | Annual Performance Plan
Goods & Services
Transformation
Output
Organisational Functionality Assessment
Productivity Measurement
Service Delivery Improvement Plan
Learning and Knowledge Management
4
Operational Forecasting
Operational Planning
Operational Control & Adjustments
3
Service Delivery Model (SM) - completed
1
Business Process Management - in progress
Standard Operating Procedure
Service Standards
Organisational Development
2
Operations Strategy
Operations Analysis & Improvement
Operations Design
Operations Planning & Control
Batho Pele
Notes: Not for presentation purposes
This is important background information that will guide managers on what the content is focusing on

## Slide 6
OMF Phase II (Workstream 2)
DCS Value Chain…..and structure
xx
STRATEGY & PLANNING
POLICY & PROGRAMMES
RISK & GOVERNANCE
MONITORING & EVALUATION
STRATEGIC PARTNERSHIPS
CENTRE OF EXCELLENCE
FINANCE
FACILITIES
ICT
HUMAN RESOURCES
SUPPLY CHAIN
THEATRE OF OPERATIONS
Providing the best Correctional Services for
a safer South Africa
CORE SERVICES
SOCIAL
RE-INTEGRATION
OPERATIONAL
INCARCERATION
REHABILITATION
SECURITY
CARE
Notes: Not for presentation purposes
This is important background information that will guide managers on what the content is focusing on

## Slide 7
OMF Phase II (Workstream 2)
Phase II Workstreams
Workstream 1: People and structure alignment
Workstream 2: Process and technology
Workstream 3: Governance
Workstream 4: Change Management
.
Workstream 5: Self sufficiency
Review the organisational structure
Conduct specialised HR exercises to define key concepts such as the ‘ideal correctional official’, the ideal culture, the competency sets required across the organisation for greater professionalisation
Deploy culture interventions
Mapping of business processes reflective of the Service Delivery Model
Incorporating workflows into standardised documentation
Input of workflows into system design and enhancement
Training for users on processes and technology
Facilitate centralisation of ICT
Update any affected policies
Update of the Delegations of Authority
Update the B-Order and ORP
Communication Strategy and Implementation Plan (Comms)
Selection and Capacitation of Change Leaders and Change Champions
Monitoring and Evaluation
Defining the value of self sufficiency in support of self sustenance and revenue generation
Production workshops
Financial sustainability
Notes: Not for presentation purposes
This is important background information that will guide managers on what the content is focusing on

## Slide 8
Sub Workstream 0 Leader (DC GITO)
Sub Workstream 1
Leader (DRC LMN)
Workstream 2
People and Technology
OMF Phase II (Workstream 2)
Composition of Workstream 2
Sub Workstream 3
Leader (DC SCM)
Sub Workstream 2
Leader (RC LMN)
Capturing of business processes for Security, Facilities and Social Reintegration
Capturing of business processes for Incarceration, Care and Rehabilitation
Capturing of business processes for support functions
System and mapping support

## Slide 9
OMF Phase II (Workstream 2)
Overview of Workstream 2 progress
Preparation and activation
Mapping of the « As-Is » processes
Determine improvement approach
Implement business processes
Mapping of « To-Be » processes
Chart: 
| 1st Qtr
Sales | 100
Chart: 
| 1st Qtr
Sales | 35
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr
Sales | 35 | 23 | 12
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr | 5th Qtr
Sales | 35 | 23 | 12 | 17 | 13
Chart: 
| 1st Qtr
Sales | 35
i.
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr | 5th Qtr
Sales | 35 | 23 | 12 | 17 | 13
ii.
iv.
v.
vi.
iii.
Monitor and maintain
100%
100%
100%
75%
17%
35%
Notes: Not for presentation purposes
This is important background information that will guide managers on what the content is focusing on

## Slide 10
OMF Phase II (Workstream 2)
Detailed progress on Workstream 2
DELIVERABLES | PROGRESS TO DATE | COMMENTS
Preparation and activation |  | 
Mapping of the “ As-Is” processes |  | 
Determine improvement approach |  | 
Mapping of “To-Be” processes |  | 
Implement business processes |  | 
Monitor and maintain |  | 
Notes: Not for presentation purposes
This is important background information that will guide managers on what the content is focusing on

## Slide 11
Head Office, CMAX, Regions
Modderbee
Pietermaritzburg
Barberton
Pollsmoor
St Albans
Grootvlei
Sub-work stream 2.1:
Incarceration, Rehabilitation and Care
Sub-work stream 2.2:
Security, Facilities and Social Reintegration
Sub-work stream 2.3:
ICT, HR, Finance & Supply Chain Management and all other Administration, Strategic Management, Legal Services, Internal Audit and Communication
13 – 14 Feb 2020
09 – 13 Dec 2019
04 – 08 Nov 2019
11 – 15 Nov 2019
18 – 22 Nov 2019
25 – 29 Nov 2019
02 – 06 Dec 2019
Detailed progress on Workstream 2 (“as-is”)
OMF Phase II (Workstream 2)

## Slide 12: At a Management Area and Centre level, different components of the SDM are being realised according to the processes with overlaps in certain areas
Management Area
Correctional Centre
External Escorting
Release
Assessment & Sentence Planning
Admission
Correctional Programmes
Psychological Services
Social Work
Spiritual Care
Wort Teams (Span)
Internal Escorting
Movement Control
Case Review
CMC Treatment & CMC Profiling
Parole Board
Access Gate Control
Watchtowers
Skills Development
Admission
Pre - Release Assessment
Formal Education
Sports & Recreation
Community Corrections
Medical Consultation
Hospital Referral
Pharmacy
Medical Screening
Medical Accounts
Kitchen Duties
Waste Management
Personal Hygiene Stock Control
Monitoring, Supervision & Treatment
Release
Care
Incarceration
Rehabilitation
Security
Social Reintegration
Perimeter Fence
OMF Phase II (Workstream 2)

## Slide 13: The current shift structure does not appear to be aligned to operational needs in many cases…
All stats are derived from personnel and offender data from 193 correctional centres
Correctional Centre Daily Programme
High security demand as inmates are moving to engage with various correctional services
Unlock
Lockup
Risk Profile
Movements (Internal & External)
External Labour & Court Movements
Skills Development
Care (Meals & Medical Services)
Low security demand as inmates are within units and/or cells
Correctional Programmes
Low security demand as inmates are within units and/or cells
High
Low
Maximum Threshold
Some centres use 12 hour shifts across 2 division while others use 8 hour shifts across 2 divisions
Additionally, CMA and CMC staff are primarily required between Unlock and Lockup but they are tied to the same shift structure as Security Officials
The high variation in shift structures across Management Areas and Centres make it difficult to optimally plan Human Resources effectively
OMF Phase II (Workstream 2)

## Slide 14: … and the variability in the staff to inmate ratio at a centre level compounds the complexity of the environment
Overall Staff: Inmate Ratio at Centre Level
Large
1:6
Medium
1:5
Small
1:2
On average large centres have a staff of inmate ratio of 1:6, however, there are a few centres that sit outside the normal range.
The centres that are the main outliers are the Calvinia and Springbok Correctional facilities, both located in the Northern Cape.
From a security ratio alone, these centres currently stand at 1:25 and 1:19 respectively.
Medium sized facilities which sit outside the average 1:5 staff to inmate ratio are both located in the Western Cape.
The Riebeeck and Hawequa Correctional facilities currently sit at a security staff to inmate 1:18 and 1: 13 respectively.
Baberton was the biggest outlier by a large margin, with the staff to inmate ratio being 1:32.
Commentary
OMF Phase II (Workstream 2)

## Slide 15: Process gaps in Incarceration are linked to ICT gaps, sharing of human resources and coordination with external stakeholders
Management Area
Correctional Centre
External Escorting
Release
Assessment & Sentence Planning
Admission
Correctional Programmes
Psychological Services
Social Work
Spiritual Care
Work Teams (Span)
Internal Escorting
Movement Control
Case Review
CMC Treatment & CMC Profiling
Parole Board
Access Gate Control
Watchtowers
Skills Development
Admission
Pre - Assessment
Formal Education
Sports & Recreation
Community Corrections
Medical Consultation
Hispanicisation
Pharmacy
Medical Screening
Medical Accounts
Kitchen Duties
Waste Management
Personal Hygiene Stock Control
Monitoring, Supervision & Treatment
Release
Monitoring, Supervision & Treatment
Care
Incarceration
Rehabilitation
Security
Social Reintegration
Perimeter Fence
Poor coordination between DCS ands SAPS regarding RD release to court
CMA shift patterns do not align with admission and release peak demand times
Unreliable ICT infrastructure and systems resulting in duplication between manual and digital processes
CMA and CMC share officials with Security. High volumes risk the quality of Incarceration processes, in particular Case Management.
Lack of identification – reoffenders may be processed as new offenders duplicating work done already impacting on the quality of sentence planning
OMF Phase II (Workstream 2)

## Slide 16: Process gaps in Security relate to non-compliance, perceived staff shortages, technology and high variability in demand for security services
Management Area
Correctional Centre
External Escorting
Release
Assessment & Sentence Planning
Admission
Correctional Programmes
Psychological Services
Social Work
Spiritual Care
Work Team (Span)
Internal Escorting
Movement Control
Case Review
CMC Treatment & CMC Profiling
Parole Board
Access Gate Control
Watchtowers
Skills Development
Admission
Assessment
Formal Education
Sports & Recreation
Community Corrections
Medical Consultation
Hospital Referral
Pharmacy
Medical Screening
Medical Accounts
Kitchen Duties
Waste Management
Personal Hygiene Stock Control
Monitoring, Supervision & Treatment
Release
Monitoring, Supervision & Treatment
Perimeter Fence
Care
Incarceration
Rehabilitation
Security
Social Reintegration
Lack of capacity to man Watchtowers and Perimeter Fencing
Movement control is not conducted according to procedure (i.e. internal buddy system lacking and inmates may move unescorted internally)
Non-standardised shift systems making human resource planning difficult
External Security is highly variable and pulls resources from internal security
Security staff perform Incarceration and Rehabilitation processes as well thus stretching the available staff
Lack of security equipment to ensure Safety
Searching internally and externally is not always actioned and conducted in a consistent manner
Technology may have been procured but not deployed (i.e. personal scanners)
OMF Phase II (Workstream 2)

## Slide 17: Process gaps in Rehabilitation are linked to sharing of human resources, insufficient security personnel and skill.
Management Area
Correctional Centre
External Escorting
Release
Assessment & Sentence Planning
Admission
Correctional Programmes
Psychological Services
Social Work
Spiritual Care
Work Team (Span)
Internal Escorting
Movement Control
Case Review
CMC Treatment & CMC Profiling
Parole Board
Access Gate Control
Watchtowers
Skills Development
Admission
Assessment
Formal Education
Sports & Recreation
Community Corrections
Medical Consultation
Hospital Referral
Pharmacy
Medical Screening
Medical Accounts
Kitchen Duties
Waste Management
Personal Hygiene Stock Control
Monitoring, Supervision & Treatment
Release
Monitoring, Supervision & Treatment
Care
Incarceration
Rehabilitation
Security
Social Reintegration
Perimeter Fence
Programme participation is limited largely by the accessibility of security officials to escort offenders
Work teams have insufficient resources to maximise productivity (personnel and assets/tools)
Performance targets for rehabilitation programmes focus more upon the completion of activities with the assumption that rehabilitation will be achieved as a result
Security officials perform certain Rehabilitation programmes but may not be sufficiently skilled to do so
OMF Phase II (Workstream 2)

## Slide 18: Process gaps in Care are linked to non-dedicated resources, ICT, facilities and staff retention
Care
Incarceration
Rehabilitation
Security
Social Reintegration
Perimeter Fence
Resources are insufficient to carry out specified care processes
Difficulty in maintaining professional service providers as DCS tariffs are non-competitive
Maintenance of health care facilities is lacking
A lack of trust in ICT systems’ reliability results in manual process duplication
Management Area
Correctional Centre
External Escorting
Release
Assessment & Sentence Planning
Admission
Correctional Programmes
Psychological Services
Social Work
Spiritual Care
Labour
Internal Escorting
Movement Control
Case Review
CMC Treatment & CMC Profiling
Parole Board
Access Gate Control
Watchtowers
Skills Development
Admission
Assessment
Formal Education
Sports & Recreation
Community Corrections
Medical Consultation
Hospital Referral
Pharmacy
Medical Screening
Medical Accounts
Kitchen Duties
Waste Management
Personal Hygiene Stock Control
Monitoring, Supervision & Treatment
Release
Resources are insufficient to carry out specified care processes
Difficulty in maintaining professional service providers as DCS tariffs are non-competitive
Maintenance of health care facilities is lacking
A lack of trust in ICT systems’ reliability results in manual process duplication
Cleanliness is self-monitored and inconsistent in application where dining areas are available
Some centres do no have functioning sub-kitchens and dining hall
Sanitary stores are managed at an ad-hoc level in some areas with poor inventory management
OMF Phase II (Workstream 2)

## Slide 19: Process gaps in Social Reintegration are linked to vehicles, volume, lack of ICT systems and community instability
Care
Incarceration
Rehabilitation
Security
Social Reintegration
Perimeter Fence
Resources are insufficient to carry out specified care processes
Difficulty in maintaining professional service providers as DCS tariffs are non-competitive
Maintenance of health care facilities is lacking
A lack of trust in ICT systems’ reliability results in manual process duplication
Management Area
Correctional Centre
External Escorting
Release
Assessment & Sentence Planning
Admission
Correctional Programmes
Psychological Services
Social Work
Spiritual Care
Labour
Internal Escorting
Movement Control
Case Review
CMC Treatment & CMC Profiling
Parole Board
Access Gate Control
Watchtowers
Skills Development
Admission
Pre - Assessment
Formal Education
Sports & Recreation
Community Corrections
Medical Consultation
Hispanicisation
Pharmacy
Medical Screening
Medical Accounts
Kitchen Duties
Waste Management
Personal Hygiene Stock Control
Monitoring, Supervision & Treatment
Release
Lack of vehicles at some offices – monitoring staff unable to conduct monitoring visits
High case loads – required monitoring visits not performed
Highly manual process – no use of technology in monitoring
Community instability resulting in reoffending
Backlog in digital migration
Pre - Release Assessment
OMF Phase II (Workstream 2)

## Slide 20
Head Office, Regions
Modderbee
Pietermaritzburg
Barberton
Pollsmoor
St Albans
Grootvlei
Sub-work stream 2.1:
Incarceration, Rehabilitation and Care
Sub-work stream 2.2:
Security, Facilities and Social Reintegration
Sub-work stream 2.3:
ICT, HR, Finance & Supply Chain Management and all other Administration, Strategic Management, Legal Services, Internal Audit and Communication
Detailed progress on Workstream 2 (“to-be”)
OMF Phase II (Workstream 2)
Jan & Feb 2021
21 – 25 Sept 2020
14 – 18 Sept 2020
05 – 09 Oct 2020
19 – 23 Oct 2020
15 – 19 Feb 2020
07 – 11 Dec 2020

## Slide 21
OMF Phase II (Workstream 2)
Remaining deliverables and timeframes
MONTH 1
Week 1
Week 2
Week 3
Week 4
START – FINISH DATE
xxx
Deliverable 1
Define HR Strategy and OD intervention
START – FINISH DATE
xx
Deliverable 2
Conduct analysis and draft Macro Structure
START – FINISH DATE
xxx
Deliverable 5
Job Descriptions
START – FINISH DATE
xx
Deliverable3
Finalisation and approval of the Micro Structure
Deliverable 4
Competency Model
START – FINISH DATE
xx
MONTH 2
Week 1
Week 2
Week 3
Week 4
MONTH 3
Week 1
Week 2
Week 3
Week 4
Deliverable 6
Job Evaluation
START – FINISH DATE
xxx
Notes: Not for presentation purposes
This is important background information that will guide managers on what the content is focusing on

## Slide 22
OMF Phase II (Workstream 2)
Risk Management
Deliverable | Strategic Risk | Risk Mitigation
Mapping of “To-Be” processes |  | 
Notes: Not for presentation purposes
This is important background information that will guide managers on what the content is focusing on

## Slide 23
OMF Phase II (Workstream 2)
Conclusion
Notes: Not for presentation purposes
This is important background information that will guide managers on what the content is focusing on

## Slide 24
THANK YOU