## Slide 1
BRANCH COMMUNITY CORRECTIONS
2020/21
PERFORMANCE TARGETS NOT ACHIEVED
2020/21
QUARTER 2

## Slide 2
PROGRAMME 5: SOCIAL REINTEGRATION SUB PROGRAMME: COMMUNITY REINTEGRATION |  |  |  |  |  |  | 
Key Performance Indicators | Q2 Target 2020/21 | Quarter 2 Performance | Reasons for under achievement | Corrective action | Timelines | Responsibility | Progress on the implementation of corrective action
Percentage increase of victims participating in Restorative Justice Programme ) | 7% | -85.76% (-10 721/12 501) | Restorative Justice processes were facilitated in line with Disaster Management Strategy (Level 2) | Implement RJ processes in line with Disaster Management Strategy (Level 1): Use of audio visual connections Review and update victims data base Use a bigger venue Market RJ continuously Letter writing Use all media platforms to market Restorative Justice processes | 2020/21 | Regional Commissioners RH Corrections Regional Coordinator SR Area Commissioners | Restorative Justice processes were facilitated in line with Disaster Management Strategy (Level 2) Use of bigger venue and Audio visual connections
INDICATORS NOT ACHIEVED DURING 2020/21 – Q2

## Slide 3
PROGRAMME 5: SOCIAL REINTEGRATION SUB PROGRAMME: COMMUNITY REINTEGRATION |  |  |  |  |  |  | 
Key Performance Indicators | Q2 Target 2020/21 | Quarter 2 Performance | Reasons for under achievement | Corrective action | Timelines | Responsibility | Progress on the implementation of corrective action
Percentage increase of offenders participating in Restorative Justice Programme ) | 3% (4176) | -74,38% (-3 016/4 055) | Restorative Justice processes were facilitated in line with Disaster Management Strategy (Level 2) | Implementation of the risk adjustment strategy (Level 1) Market RJ continuously RJ Forums to be fully effective | 2020/2021 | Regional Commissioners RH Corrections Regional Coordinator SR Area Commissioners | Restorative Justice processes were facilitated in line with Disaster Management Strategy (Level 2)
INDICATORS NOT ACHIEVED DURING 2020/21 – Q2

## Slide 4
SOURCE OF UNDER-ACHIEVEMENT AT REGIONAL LEVEL:
(Percentage increase of victims participating in Restorative Justice Programme )
Q2 TARGET 2020/21 | QUARTER 2 PERFORMANCE | REGION THAT CONTRIBUTED TOWARDS UNDER-ACHIEVEMENT | REASONS FOR UNDER PERFORMANCE | ROOT CAUSES | ASSOCIATED RISKS
(1073) 7% | 9 (-99.16%) | W.C | Lockdown has resulted in that no Restorative justice engagement occurred during the first quarter | COVID 19 pandemic and Lockdown regulations | Increased community violence Victim dissatisfaction and complaint
(1550) 7% | 264 (-88.97%) | E.C | VOD Activities were suspended due to COVID-19 pandemic |  | 
(1621) 7% | 294(-81.86%) | KZN | Due to COVID-19 Regulations Restorative Justice programmes remained suspended as well as contact sessions with parolees /probationers could not be conducted effectively. |  | 
(1981) 7% | 306(-84.76%) | FS/NC | Due to COVID-19 Regulations Restorative Justice programmes remained suspended as well as contact sessions with parolees /probationers could not be conducted effectively |  | 
(4249) 7% | 353(-91.69%) | LMN | Target not achieved due to the suspension of RJ because of lockdown |  | 
(2027) 7% | 554(-72.67%) | GP | VOD Activities were suspended due to COVID-19 pandemic |  | 

## Slide 5
SOURCE OF UNDER-ACHIEVEMENT AT REGIONAL LEVEL
(Percentage increase of offenders participating in Restorative Justice Programme )
Q2 TARGET 2020/21 | QUARTER 2 PERFORMANCE | REGION THAT CONTRIBUTED TOWARDS UNDER-ACHIEVEMENT | REASONS FOR UNDER PERFORMANCE | ROOT CAUSES | ASSOCIATED RISKS
536 | 5 (-99.04%) | W.C | Lockdown has resulted in that no restorative justice engagements occurred during the 1st quarter | COVIC 19 Pandemic and Lockdown regulations | Increased complaints from inmates Increased security incidents Increased reoffending
422 | 84(-79.51%) | KZN | Restorative Justice Programme suspended due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres) |  | 
656 | 128(-79.91%) | E.C | Due to COVID-19 Regulations Restorative Justice programmes remained suspended as well as contact sessions with parolees/ probationers could not be conducted effectively. |  | 
627 | 204(-66.50%) | GP | VOD Activities were suspended due to COVID-19 pandemic |  | 
857 | 359(-72.26%) | FS/NC | Due to COVID-19 Regulations and lockdown protocols, Restorative Justice programmes and Imbizos remained suspended and contact sessions with victims could not be conducted. |  | 
1078 | 259(-56.85%) | LMN | The suspension of RJ process during the months of July and August |  | 

## Slide 6: SUMMARY OF IMPROVEMENTS FOR Q2
SUMMARY OF IMPROVEMENTS FOR Q2
The following options can be explored to improve on restorative justice:
Connection of Audio Visual should be considered.
Review and update victims data base continuously.
Tracing of victims must be a collective effort.
RJ Forums to be fully effective (quantify and qualify performance).
Involve all media platforms to continuously market RJ at all levels.
A bigger venue to accommodate social distancing with less participants in the room to be considered, within COVID-19 regulations.
A letter writing exercise should also be explored.

## Slide 7
Thank You
THANK YOU
STRIVING FOR A SOUTH AFRICA IN WHICH PEOPLE ARE AND FEEL SAFE