## Slide 1: Presentation on DCS 2nd Quarter Actual Performance Report (2016/2017) November 2016
PRESENTATION ON Q2 PERFORMANCE
HR BRANCH
24 NOVEMBER 2020

## Slide 2
2020/21
PERFORMANCE TARGETS NOT ACHIEVED
2020/21
QUARTER 2

## Slide 3: Notes to the presentation
Regions to focus on targets not achieved for Quarter 2 (cumulatively since Q1)
Reports should indicate what was planned against what was not achieved
Include under achievement at source (Regions)
Identify root causes of the under achievement and associated risks
Explain the corrective actions required in a projectised approach (i.e. what needs to be done, when and by whom, when is the target expected to be achieved)
What are the long term solutions to ensure that the problems identified do not reoccur

## Slide 4
PROGRAMME 1: ADMINISTRATION

## Slide 5
PROGRAMME 1: ADMINISTRATION SUB PROGRAMME: HUMAN RESOURCES |  |  |  |  |  |  | 
Key Performance Indicators | Q2 Target 2020/21 | Quarter 2 Performance | Reasons for under achievement | Corrective action | Timelines | Responsibility | Progress on the implementation of corrective action
Approved Integrated Human Resource Strategy | Draft Integrated HR Strategy | Master plans of each Chief Directorate developed and consolidated | Resources were directed to manage the impact of Covid-19 and implementation of response strategies. Master plans for each Chief directorate were developed and consolidated to facilitate the development of the draft Integrated HR Strategy. | Process will be accelerated to ensure the draft is concluded and consultations are done by the end of Quarter 3. | 3rd Quarter | CDC HR | The process to develop the draft IHRS has been fastracked resulting to the first draft been developed
INDICATORS NOT ACHIEVED DURING 2020/21 – Q2

## Slide 6
PROGRAMME 1: ADMINISTRATION SUB PROGRAMME: HUMAN RESOURCES |  |  |  |  |  |  | 
Key Performance Indicators | Q2 Target 2020/21 | Quarter 2 Performance | Reasons for under achievement | Corrective action | Timelines | Responsibility | Progress on the implementation of corrective action
Percentage of youth employed within the Department | 20% | 15.65% (6 072/38 808) | Recruitment processes were suspended during Lockdown Alert Levels 5 to 3. This created a backlog on the planned Recruitment processes. The Directive from DPSA to resume Recruitment processes for the advertisement of only critical and essential posts, was received in July 2020. | The Department has signed a MOU with SANDF to absorb their Reservists. Regions have appointed them and are in the process of training them. The relaxation of Lockdown restrictions permits normal Recruitment processes. | 4th Quarter | CDC HR RH: HR Dir: HR A & U | Appointment of SANDF officials is activated in Regions Regions have advertised critical and essential posts and the appointment of youth will be considered.
INDICATORS NOT ACHIEVED DURING 2020/21 – Q2

## Slide 7
PROGRAMME 1: ADMINISTRATION SUB PROGRAMME: HUMAN RESOURCES |  |  |  |  |  |  | 
Key Performance Indicators | Q2 Target 2020/21 | Quarter 2 Performance | Reasons for under achievement | Corrective action | Timelines | Responsibility | Progress on the implementation of corrective action
Percentage compliance to the EE plan in the filling of positions | SMS M = 50% F = 50% MMS M = 50% F = 50% PWDs 2% | SMS M =53.21 F= 46.79 MMS M=49.50 F =50.50 PWD 0.77 | Applications for deviation from the EE Targets are continuously accommodated by the delegated authority | Delegated authority should comply consistently with EE targets when filling vacant positions | 3rd Quarter | Chief Operations Commissioner | Constant reminder to the delegated authority and monitoring of compliance to EE Targets by all functionaries
INDICATORS NOT ACHIEVED DURING 2020/21 – Q2

## Slide 8
SOURCE OF UNDER-ACHIEVEMENT AT REGIONAL LEVEL
Q2 TARGET 2020/21 | QUARTER 2 PERFORMANCE | REGION THAT CONTRIBUTED TOWARDS UNDER-ACHIEVEMENT | REASONS FOR UNDER PERFORMANCE | ROOT CAUSES | ASSOCIATED RISKS
20% of youth employed within the Department | 15.65% | EC FSNC GP KZN LMN WC | Suspension of all Recruitment processes during Covid-19 Lockdown Alert Levels 3,4 and 5 | Global Covid-19 pandemic outbreak whereby DPSA issued directives to all Departments to suspend their Recruitment and Selection processes which was only resumed during July 2020. | Inability to fill vacant positions timeously High vacancy rate which will lead to budget cuts on the CoE Budget
Percentage compliance to the EE Plan in the filling of positions SMS M (50%) F (50%) MMS M (50%) F (50%) PWD’s (2%) | SMS M (53.21%) F (46.79%) MMS M (49.50%) F (50.50%) PWD’s (0.77%) | EC FSNC GP KZN LMN WC | Suspension of all Recruitment processes during Covid-19 Lockdown Alert Levels 3,4 and 5 | Global Covid-19 pandemic outbreak whereby DPSA issued directives to all Departments to suspend their Recruitment and Selection processes which was only resumed during July 2020. | Inability to fill vacant positions timeously High vacancy rate which will lead to budget cuts on the CoE Budget

## Slide 9: SUMMARY OF IMPROVEMENTS FOR Q2
Number of Covid-19 Awareness sessions over- achieved due to the demand for training that exceeds the plan.
There was an increase in the appointment of SANDF Youth Reservists towards the end of Quarter 2 which will lead to over-achievement in quarter 3.
Mandate to negotiate with labour about the universal shift system has been obtained
The process to develop the draft IHRS has been fastracked resulting to the first draft been developed

## Slide 10
Thank You
THANK YOU
STRIVING FOR A SOUTH AFRICA IN WHICH PEOPLE ARE AND FEEL SAFE