## Slide 1
2020 ANNUAL STRATEGIC PLANNING SESSION
OMF PHASE II
WORKSTREAM 3

## Slide 2
Presentation outline
1 | Purpose
2 | Legislative framework
3 | Public Service Operations Management Framework
4 | DCS Value Chain
5 | Composition of Work Streams & sub - work streams
6 | Progress Workstream deliverables
7 | Planned deliverables and timeframes
8 | Conclusion

## Slide 3
OMF Phase II (Workstream 3)
Purpose
The purpose of the presentation is to:
Provide context to the DCS Operations Management Framework Phase II with a focus on the deliverables of Work-stream 3: Governance framework and policies.
Provide a summary of the guiding prescripts, guidelines, policy mandates that inform the work to be delivered by Work-stream 3: Governance framework and policies.
Indicate the core members of Work-stream 3: Governance framework and policies that have been appointed to deliver on Phase II.
Provide progress of the work completed by Work-stream 3: Governance framework and policies since the appointment of the work-stream leaders and members in February 2019 (18 months).
Indicate the outstanding deliverables for Work-stream 3: Governance framework and policies with timeframes against the OMF Phase II Charter.
Provide concluding remarks on the deliverables of Work-stream 3: Governance framework and policies and the movement into the next phase.
Notes: Not for presentation purposes
This is important background information that will guide managers on what the content is focusing on

## Slide 4
OMF Phase II (Workstream 3)
Legislative framework - Workstream 3
  Key legislations/best practices/regulations that regulates DCS:-
  a) Public Finance Management Act 1 of 1999 (as amended);
  b) Treasury Regulations, 2005
  c) National Treasury Instructions.
  d) DCS Internal policies .
  e) King IV Report.
  f) DCS Governance structures
  g) Correctional Services Act 111 of 1998.
  h) White Paper on Corrections.
  i) White Paper on Remand Detention.
Notes: Not for presentation purposes
This is important background information that will guide managers on what the content is focusing on

## Slide 5
OMF Phase II (Workstream 3)
DCS Operations Management Framework
DCS STRATEGY
OPERATIONS
Transformed Resources
Material
Information
Service Beneficiaries
Transformed Resources
Facilities
Officials
National Development Plan | Medium-Term Strategic Framework | Strategic plan | Annual Operational Plan | Annual Performance Plan
Goods & Services
Transformation
Output
Organisational Functionality Assessment
Productivity Measurement
Service Delivery Improvement Plan
Learning and Knowledge Management
4
Operational Forecasting
Operational Planning
Operational Control & Adjustments
3
Service Delivery Model (SM) - completed
1
Business Process Management - in progress
Standard Operating Procedure
Service Standards
Organisational Development
2
Operations Strategy
Operations Analysis & Improvement
Operations Design
Operations Planning & Control
Batho Pele
Notes: Not for presentation purposes
This is important background information that will guide managers on what the content is focusing on

## Slide 6
OMF Phase II (Workstream 3)
DCS Value Chain…..and structure
xx
STRATEGY & PLANNING
POLICY & PROGRAMMES
RISK & GOVERNANCE
MONITORING & EVALUATION
STRATEGIC PARTNERSHIPS
CENTRE OF EXCELLENCE
FINANCE
FACILITIES
ICT
HUMAN RESOURCES
SUPPLY CHAIN
THEATRE OF OPERATIONS
Providing the best Correctional Services for
a safer South Africa
CORE SERVICES
SOCIAL
RE-INTEGRATION
OPERATIONAL
INCARCERATION
REHABILITATION
SECURITY
CARE
Notes: Not for presentation purposes
This is important background information that will guide managers on what the content is focusing on

## Slide 7
OMF Phase II (Workstream 3)
Phase II Workstreams
Workstream 1: People and structure alignment
Workstream 2: Process and technology
Workstream 3: Governance
Workstream 4: Change Management
.
Workstream 5: Self sufficiency
Review the organisational structure
Conduct specialised HR exercises to define key concepts such as the ‘ideal correctional official’, the ideal culture, the competency sets required across the organisation for greater professionalisation
Deploy culture interventions
Mapping of business processes reflective of the Service Delivery Model
Incorporating workflows into standardised documentation
Input of workflows into system design and enhancement
Training for users on processes and technology
Facilitate centralisation of ICT
Update any affected policies
Update the Delegations of Authority
Update the B-Order and ORP
Communication Strategy and Implementation Plan (Comms)
Selection and Capacitation of Change Leaders and Change Champions
Monitoring and Evaluation
Defining the value of self sufficiency in support of self sustenance and revenue generation
Production workshops
Financial sustainability
Notes: Not for presentation purposes
This is important background information that will guide managers on what the content is focusing on

## Slide 8
Workstream Leader
DC ICC
DC Policy Coordination and Research
Director Information
Management
Workstream 3
Governance framework and policies
Director Risk
Management
Director Inspectorate
Act Director Contract Management
Director Policy and
Procedure Coordination
Director Research
OMF Phase II (Workstream 3)
Composition of Workstream 3
Director Legal Contract Management
Director Code Enforcement

## Slide 9
OMF Phase II (Workstream 3)
Overview of Workstream 3 progress
Update any affected policies
Update the Delegations of Authority
Update the B-Order and ORP
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr | 5th Qtr
Sales | 35 | 23 | 12 | 17 | 13
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr | 5th Qtr
Sales | 35 | 23 | 12 | 17 | 13
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr | 5th Qtr
Sales | 35 | 23 | 12 | 17 | 13
i.
ii.
iii.
75%
100%
85%
Notes: Not for presentation purposes
This is important background information that will guide managers on what the content is focusing on

## Slide 10
OMF Phase II (Workstream 3)
Detailed progress on Workstream 3
DELIVERABLES | PROGRESS TO DATE | COMMENTS
Update any affected policies | Policies relating to Finance, SCM and core business policies were drafted and forwarded for final approval. | Team to align to B-order and other delegations once finalized.
Update the Delegations of Authority | Delegations were updated. | None
Update the B-Order and ORP | The B-Order document was reviewed. COC team responsible for B-Order. The process is at the stage were draft was forwarded further inputs | Awaiting final document on B-Order align to ORP.
Notes: Not for presentation purposes
This is important background information that will guide managers on what the content is focusing on

## Slide 11
OMF Phase II (Workstream 3)
Remaining deliverables and timeframes
START – FINISH DATE 1 Jan- Mar 2021
Deliverable 1
Update relevant policies
START – FINISH DATE 1 Jan- Mar 2021
Deliverable 2
Update the Delegations of Authority
START – FINISH DATE 1 Jan- Mar 2021
Deliverable3
Update the B-Order and ORP
QUARTER 2
Month 1
Month 2
Month 3
QUARTER 1
Month 1
Month 2
Month 3
QUARTER 3
Month 1
Month 2
Month 3
QUARTER 4
Month 1
Month 2
Month 3
Notes: Not for presentation purposes
This is important background information that will guide managers on what the content is focusing on

## Slide 12
OMF Phase II (Workstream 3)
Risk Management
Deliverable |  |  | Strategic Risk |  |  | Risk Mitigation |  | 
1.Update affected policies, delegations, B-Order and ORP |  |  | 1.Misalignment of governance frameworks(policies, structures, etc.) to departmental mandates. |  |  | 1. Extensive and in-depth consultation amongst work-stream teams. |  | 
 |  |  | 2. Lack of management buy-in |  |  | 1.Change Management |  | 
 |  |  |  |  |  | 2. Engagement sessions and workshops |  | 
 |  |  | 3. Conflicting priorities |  |  | Extensive consultation between affected work-streams and management. |  | 
Notes: Not for presentation purposes
This is important background information that will guide managers on what the content is focusing on

## Slide 13
OMF Phase II (Workstream 3)
Conclusion
Alignment and integration of work amongst work-streams is critical to ensure success in respect of the implementation of OMF within the department.
Management has note the challenges imposed by intra- and/or inter-dependencies between the work-stream deliverables affecting project timelines. E.g. Updating of policies is extremely dependent on the finalization of the review of organization processes.
The intra- and/or inter dependencies poses challenge in respect of meeting deadlines by different work-streams. In addition, the challenge of deadlines is also compounded by changes in work-stream compositions. E.g. Work-stream 3 has several resignations which then affect continuity.
Notes: Not for presentation purposes
This is important background information that will guide managers on what the content is focusing on

## Slide 14
THANK YOU