## Slide 1
NATIONAL MANAGEMENT QUARTERLY
PERFORMANCE REVIEW:
KZN REGION
Presented by: DC TK Mthombeni
Date: 24 November 2020

## Slide 2
2020/21
PERFORMANCE TARGETS NOT ACHIEVED DURING QUARTER 2

## Slide 3
Total No of Mid term Targets per MA | Achieved | Not Achieved | Target measured annually /per academic year
25 | 18 | 07 | 02
Mid-term Performance Report on Performance indicators 2019/20
Total Nor of targets
Total Nor of targets
Chart: 
| Achieved | Not Achieved | Measured per academic year /Annually.
Overall Q1 Performance Configuration | 0.8846 | 0.0769 | 0.0385

## Slide 4
PROGRAMME 2
INCARCERATION

## Slide 5
PERFORMANCE INDICATOR NOT ACHIEVED:
Percentage of inmates injured as a result of reported assaults in Correctional Facilities
1. REGIONAL TARGET VERSUS PERFORMANCE FOR 2nd QUARTER (2020/2021)
2. SOURCE OF UNDER-ACHIEVEMENT AT MANAGEMENT AREA LEVEL
REGION | JULY 2020 TARGET | JULY PERFORMANCE | AUGUST 2020 TARGET | AUGUST PERFORMANCE | SEPTEMBER 2020 TARGET | SEPTEMBER PERFORMANCE | Q2 TARGET: 2020-2021 | PERFORMANCE
Kwa Zulu Natal | 392/25120 = 1.56% | 305/22173 = 1.38% | 495/25120 = 1.97% | 455/21851 = 2.08% | 593/25120 = 2.36% | 537/22009 = 2.44% | 2.33% | 537/22009 = 2.44%
MANAGEMENT AREA | JULY 2020 TARGET | JULY PERFORMANCE | AUGUST 2020 TARGET | AUGUST PERFORMANCE | SEPTEMBER 2020 TARGET | SEPTEMBER PERFORMANCE | Q2 TARGET: 2020-2021 | PERFORMANCE
Durban | 124/7884 = 1.57% | 177/7608 = 2.33% | 155/7884 = 1.97% | 47/1620 = 2.90% | 186/7884 = 2.36% | 318/7163 = 1.44% | 186/7884 = 2.36% | 318/7163 = 1.44%
Glencoe | 32/2106 = 1.52% | 27/1651 = 1.64% | 268/7381 = 3.63% | 45/2230 = 2.02% | 49/2106 = 2.33% | 48/2252 = 2.34% | 49/2106 = 2.33% | 48/2252 = 2.34%
Waterval | 36/2230 = 1.61% | 24/1716 = 1.40% | 41/2106 = 1.95% | 46/1762 = 2.61% | 54/2230 = 2.42% | 50/1800 = 2.78% | 54/2230 = 2.42% | 50/1800 = 2.78%

## Slide 6
3. SOURCE OF UNDER-ACHIEVEMENT AT CORRECTIONAL CENTRE LEVEL MANAGEMENT AREA TO POPULATE
Q2 TARGET 2020/21 | QUARTER 2 PERFORMANCE | MANAGEMENT AREAS THAT CONTRIBUTED TOWARDS UNDER-ACHIEVEMENT | CORRECTIONAL CENTRE | REASONS FOR UNDER PERFORMANCE | ROOT CAUSES | ASSOCIATED RISKS
186/7884 = 2.36% | 318/7163 = 1.44% | Durban | 1. Remand Detention Facility 2. Maximum | Offenders were under lot of stress during lockdown and they tend to become irritable with each other. Suspension of visits caused the anxiety Uncertainty about if hey will survive Covid - 19 | Covid 19 Risk Adjusted Strategy Regulation are not relaxed | Mass riot between gang members, Escapes Unnatural deaths
49/2106 = 2.33% | 48/2252 = 2.34% | Glencoe | Glencoe Escourt | During the month of August 2020 gang related violent activities were rife emanating from the death of an offender at Glencoe Correctional Centre. Movement of offenders from bigger centres also contributed to the increase in gang related violent incidents | Covid 19 Risk Adjusted Strategy Regulation are not relaxed | Mass riot between gang members, Escapes Unnatural deaths
54/2230 = 2.42% | 50/1800 = 2.78% | Waterval | 1. Waterval med. A 2. Waterval med. B | Movement of offenders from bigger centres to Farm correctional centres triggered gangsterism Gang related assaults amongst sentenced offenders and remand detainees. | Some offenders are still active and practicing gangsterism despite the fact that gang management strategy has been implemented. During level five Covid -19 regulation period offenders were frustrated because of tobacco unavailability. | Mass riot between gang members, Escapes Unnatural deaths
PERFORMANCE INDICATOR NOT ACHIEVED:
Percentage of inmates injured as a result of reported assaults in Correctional Facilities

## Slide 7
4. DURBAN PROJECT PLAN TO ADDRESS UNDER PERFORMANCE – MANAGEMENT AREA TO
POPULATE
MANAGEMENT AREA | CORRECTIONAL CENTRE | ACTIVITY / ACTIVITIES | RESPONSIBILITY | TIME FRAME | PROGRESS
Durban | 1. Remand Detention Facility 2. Maximum | Resensitize officials on the implementation of the Anti Gang Strategy. Identify hotspots (sections) where assaults are rife. Control the movement of offenders during feeding. (feeding in batches of groups) Placement of food trolleys closer to cells being fed to minimise distance to be travelled. Combine available sections (officials present) to beef up security in the sections. Control and separate foreign nationals. Increase surprise searching of cells Manage the complaints and requests of offenders. Ensure the availability of the Dog Unit and EST during feeding | Area Commissioner / Area Coordinator Corrections / Manager Security/ Head of Centre/ CC Ops/ CC Staff Support/ DH Security/ Unit Managers/ Supervisors | October 2020 and ongoing | Anti Gang Strategy implemented. Hotspots are closely monitored. Offender movement controlled. Surprise searches have been increased. Complaints and requests are being attended to. EST and Dog Unit is made available during feeding.
PLAN TO ADDRESS UNDER PERFORMANCE:
Percentage of inmates injured as a result of reported assaults in Correctional Facilities

## Slide 8
4. PROJECT PLAN TO ADDRESS UNDER PERFORMANCE – MANAGEMENT AREA TO POPULATE
MANAGEMENT AREA | CORRECTIONAL CENTRE | ACTIVITY / ACTIVITIES | RESPONSIBILITY | TIME FRAME | PROGRESS
Glencoe |  | Prevention of assaults and injuries Surprise visits by Executive management. Reopening of Recreational activities. Marketing of Educational programmes Visitations reopened Surprise searches | Area Commissioner / Area Coordinator Corrections / Manager Security/ Head of Centre/ CC Ops/ CC Staff Support/ DH Security/ Unit Managers/ Supervisors | October 2020 and ongoing | Assault Prevention Plans have been implemented. Visits by some Executive Management members Visitation reopened with close monitoring of visitors. Recreational activities arranged to keep inmates recreationally busy. Participation in Educational has been marketed
Waterval | 1. Waterval med. A 2. Waterval med. B | Effective implementation of Gang management strategy , continue to hold security meetings . Close monitoring of offenders. Proper handling of requests s and complaints. | Area Commissioner / Area Coordinator Corrections / Manager Security/ Head of Centre/ CC Ops/ CC Staff Support/ DH Security/ Unit Managers/ Supervisors | October 2020 and ongoing | Gang management strategy has been implemented. Movement of offenders within Units is being monitored Complaints and requests from offenders are being attended and responded to.
PLAN TO ADDRESS UNDER PERFORMANCE:
Percentage of inmates injured as a result of reported assaults in Correctional Facilities

## Slide 9
PROGRAMME 3
REHABILITATION

## Slide 10
PERFORMANCE INDICATOR NOT ACHIEVED:
Percentage of offenders participating in GET per academic year
1. REGIONAL TARGET VERSUS PERFORMANCE FOR 2nd QUARTER (2020/2021)
2. SOURCE OF UNDER-ACHIEVEMENT AT MANAGEMENT AREA LEVEL
REGION | APRIL 2020 TARGET | APRIL PERFORMANCE | MAY 2020 TARGET | MAY PERFORMANCE | JUNE 2020 TARGET | JUNE PERFORMANCE | Q2 TARGET: 2020-2021 | PERFORMANCE
Kwa Zulu Natal | 1026/1282 = 80.003% | 69/69 = 100% | 1026/1282 = 80.03% | 40/84 = 47.62% | 1026/1282 = 80.03% | 265/562 =47.155 | 80% | 125/238 = 52.31%
MANAGEMENT AREA | APRIL 2020 TARGET | APRIL PERFORMANCE | MAY 2020 TARGET | MAY PERFORMANCE | JUNE 2020 TARGET | JUNE PERFORMANCE | Q2 TARGET: 2020-2021 | PERFORMANCE
Durban | 262/327 = 80.12% | 69/69 = 100% | 262/327 = 80.12% | 0/0 = 0.00% | 262/327 = 80.12% | 30/75 = 40% | 0/0 = 0.00% | 0/0 = 0.00%
Empangeni | 160/200 = 80% | 0/0 = 0.00% | 160/200 = 80% | 0/0 = 0.00% | 160/200 = 80% | 60/200 = 30% | 0/0 = 0.00% | 0/0 = 0.00%
Glencoe | 56/70 = 80% | 0/0 = 0.00% | 56/70 = 80% | 0/0 = 0.00% | 56/70 = 80% | 24/27 = 88089% | 0/0 = 0.00% | 0/0 = 0.00%

## Slide 11
PERFORMANCE INDICATOR NOT ACHIEVED:
Percentage of offenders participating in GET per academic year
2. SOURCE OF UNDER-ACHIEVEMENT AT MANAGEMENT AREA LEVEL
MANAGEMENT AREA | APRIL 2020 TARGET | APRIL PERFORMANCE | MAY 2020 TARGET | MAY PERFORMANCE | JUNE 2020 TARGET | JUNE PERFORMANCE | Q2 TARGET: 2020-2021 | PERFORMANCE
Kokstad | 148/185 = 80% | 0/0 = 0.00% | 148/185 = 80% | 0/0 = 0.00% | 148/185 = 80% | 55/148 = 37.16% | 0/0 = 0.00% | 0/0 = 0.00%
Ncome | 220/275 = 80% | 0/0 = 0.00% | 220/275 = 80% | 40/84 = 47.62% | 220/275 = 80% | 36/52 = 69.23% | 0/0 = 0.00% | 0/0 = 0.00%
Pietermaritzburg | 124/155 = 80% | 0/0 = 0.00% | 124/155 = 80% | 0/0 = 0.00% | 124/155 = 80% | 48/48 = 100% | 0/0 = 0.00% | 0/0 = 0.00%
Waterval | 56/70 = 80% | 0/0 = 0.00% | 56/70 = 80% | 0/0 = 0.00% | 56/70 = 80% | 12/12 = 100% | 0/0 = 0.00% | 0/0 = 0.00%

## Slide 12
3. SOURCE OF UNDER-ACHIEVEMENT AT CORRECTIONAL CENTRE LEVEL MANAGEMENT AREA TO
POPULATE
Q2 TARGET 2020/21 | QUARTER 2 PERFORMANCE | MANAGEMENT AREAS THAT CONTRIBUTED TOWARDS UNDER-ACHIEVEMENT | CORRECTIONAL CENTRE | REASONS FOR UNDER PERFORMANCE | ROOT CAUSES | ASSOCIATED RISKS
0/0 = 0.00% | 0/0 = 0.00% | Durban | Youth Centre CC - Usethubeni | Only AET Level 4 was in attendance during the months | Covid 19 Risk Adjusted Strategy Regulation | Offenders not attending classes may resort to gangsterism which will increase the number of assaults and unnatural deaths
0/0 = 0.00% | 0/0 = 0.00% | Empangeni | Qalakabusha CC | Only AET Level 4 was in attendance during the months | Covid 19 Risk Adjusted Strategy Regulation | Offenders not attending classes may resort to gangsterism which will increase the number of assaults and unnatural deaths
0/0 = 0.00% | 0/0 = 0.00% | Glencoe | Glencoe CC Escourt CC | Only AET Level 4 was in attendance during the months | Covid 19 Risk Adjusted Strategy Regulation | Offenders not attending classes may resort to gangsterism which will increase the number of assaults and unnatural deaths
PERFORMANCE INDICATOR NOT ACHIEVED:
Percentage of offenders participating in GET per academic year

## Slide 13
3. SOURCE OF UNDER-ACHIEVEMENT AT CORRECTIONAL CENTRE LEVEL MANAGEMENT AREA TO POPULATE
Q2 TARGET 2020/21 | QUARTER 2 PERFORMANCE | MANAGEMENT AREAS THAT CONTRIBUTED TOWARDS UNDER-ACHIEVEMENT | CORRECTIONAL CENTRE | REASONS FOR UNDER PERFORMANCE | ROOT CAUSES | ASSOCIATED RISKS
0/0 = 0.00% | 0/0 = 0.00% | Kokstad | Ebongweni CC Kokstad Medium CC Port Shepstone | In line with Covid-19 lockdown regulations, only Level four learners attended classes. | Covid 19 Risk Adjusted Strategy Regulation | Offenders not attending classes may resort to gangsterism which will increase the number of assaults and unnatural deaths
0/0 = 0.00% | 0/0 = 0.00% | Ncome | All the Centres | Only AET Level 4 was in attendance during the months | Covid 19 Risk Adjusted Strategy Regulation | Offenders not attending classes may resort to gangsterism which will increase the number of assaults and unnatural deaths
0/0 = 0.00% | 0/0 = 0.00% | Pietermaritzburg | Medium A Medium B Sevontein | Only AET Level 4 was in attendance during the months | Covid 19 Risk Adjusted Strategy Regulation | Offenders not attending classes may resort to gangsterism which will increase the number of assaults and unnatural deaths
0/0 = 0.00% | 0/0 = 0.00% | Waterval | All the Centres | Only AET Level 4 was in attendance during the months | Covid 19 Risk Adjusted Strategy Regulation | Offenders not attending classes may resort to gangsterism which will increase the number of assaults and unnatural deaths.
PERFORMANCE INDICATOR NOT ACHIEVED:
Percentage of offenders participating in GET per academic year

## Slide 14
4. PROJECT PLAN TO ADDRESS UNDER PERFORMANCE – MANAGEMENT AREA TO POPULATE
MANAGEMENT AREA | CORRECTIONAL CENTRE | ACTIVITY / ACTIVITIES | RESPONSIBILITY | TIME FRAME | PROGRESS
Durban | All Correctional Centres | Effective marketing of GET educational programme | Area Coordinator Dev & Care and Regional Head Dev & Care | October 2020 and ongoing | Phasing in of other levels be resumed in line with the DCS COVID-19 risk adjusted strategy
Kokstad | All Correctional Centres | Effective marketing of GET educational programme | Area Coordinator Dev & Care and Regional Head Dev & Care | October 2020 and ongoing | Phasing in of other levels be resumed in line with the DCS COVID-19 risk adjusted strategy
Waterval | All Correctional Centres | Effective marketing of GET educational programme | Area Coordinator Dev & Care and Regional Head Dev & Care | October 2020 and ongoing | Phasing in of other levels be resumed in line with the DCS COVID-19 risk adjusted strategy
PLAN TO ADDRESS UNDER PERFORMANCE:
Percentage of offenders participating in GET per academic year

## Slide 15
4. PROJECT PLAN TO ADDRESS UNDER PERFORMANCE – MANAGEMENT AREA TO POPULATE
MANAGEMENT AREA | CORRECTIONAL CENTRE | ACTIVITY / ACTIVITIES | RESPONSIBILITY | TIME FRAME | PROGRESS
Kokstad | All Correctional Centres | Effective marketing of GET educational programme | Area Coordinator Dev & Care and Regional Head Dev & Care | October 2020 and ongoing | Phasing in of other levels be resumed in line with the DCS COVID-19 risk adjusted strategy
Ncome | All Correctional Centres | Effective marketing of GET educational programme | Area Coordinator Dev & Care and Regional Head Dev & Care | October 2020 and ongoing | Phasing in of other levels be resumed in line with the DCS COVID-19 risk adjusted strategy
Pietermaritzburg | All Correctional Centres | Effective marketing of GET educational programme | Area Coordinator Dev & Care and Regional Head Dev & Care | October 2020 and ongoing | Phasing in of other levels be resumed in line with the DCS COVID-19 risk adjusted strategy
Waterval | All Correctional Centres | Effective marketing of GET educational programme | Area Coordinator Dev & Care and Regional Head Dev & Care | October 2020 and ongoing | Phasing in of other levels be resumed in line with the DCS COVID-19 risk adjusted strategy
PLAN TO ADDRESS UNDER PERFORMANCE:
Percentage of offenders participating in GET per academic year

## Slide 16
PERFORMANCE INDICATOR NOT ACHIEVED:
Percentage of inmates receiving spiritual care services
1. REGIONAL TARGET VERSUS PERFORMANCE FOR 2nd QUARTER (2020/2021)
2. SOURCE OF UNDER-ACHIEVEMENT AT MANAGEMENT AREA LEVEL
REGION | JULY 2020 TARGET | JULY PERFORMANCE | AUGUST 2020 TARGET | AUGUST PERFORMANCE | SEPTEMBER 2020 TARGET | SEPTEMBER PERFORMANCE | Q2 TARGET: 2020-2021 | PERFORMANCE
Kwa Zulu Natal | 2006/30090 = 6.67% | 760/22164 = 3.42% | 2006/30090 = 6.67% | 872/21851 = 3.99% | 2006/30090 = 6.67% | 1436/22009 = 6.52% | 40% | 5 143/22 009 = 23.37%
MANAGEMENT AREA | JULY 2020 TARGET | JULY PERFORMANCE | AUGUST 2020 TARGET | AUGUST PERFORMANCE | SEPTEMBER 2020 TARGET | SEPTEMBER PERFORMANCE | Q2 TARGET: 2020-2021 | PERFORMANCE
Durban | 662/9930 = 6.67% | 95/7604 = 1.25% | 662/9930 = 6.67% | 159/73 81 = 2.15% | 662/9930 = 6.67% | 285/7163 = 3.98% | 3972/9930 = 40% | 684/7163 = 9.55%
Empangeni | 273/4098 = 6.66% | 62/2875 = 2.16% | 273/4098 = 6.66% | 43/2895 =1.49% | 273/4098 = 6.66% | 171/2878 = 5.98% | 1638/4098 = 39.97% | 376/2878 = 13.06%
Glencoe | 160/2407 = 6.65% | 241/1649 = 14.61% | 160/2407 = 6.65% | 222/1620 = 13.70% | 160/2407 = 6.65% | 283/2052 = 13.79% | 960/2407 = 39% | 1442/2052 = 70.27%
Kokstad | 140/2106 = 6,65% | 169/1537 = 11% | 140/2106 = 6,65% | 195/1534 = 12.71% | 140/2106 = 6,65% | 258/1605 = 16.07% | 840/2106 = 39.89% 846/2106=40.17% | 1030/1605 = 64.17% 1089/1605=68.85% Difference of 59 is with Q1 at Regional office

## Slide 17
PERFORMANCE INDICATOR NOT ACHIEVED:
Percentage of inmates receiving spiritual care services
2. SOURCE OF UNDER-ACHIEVEMENT AT MANAGEMENT AREA LEVEL (CONT…)
MANAGEMENT AREA | JULY 2020 TARGET | JULY PERFORMANCE | AUGUST 2020 TARGET | AUGUST PERFORMANCE | SEPTEMBER 2020 TARGET | SEPTEMBER PERFORMANCE | Q2 TARGET: 2020-2021 | PERFORMANCE
Ncome | 191/2865 = 6.67% | 185/2105 = 8.79% | 191/2865 = 6.67% | 167/2045 =8.17% | 191/2865 = 6.67% | 214/1963 = 10,93% | 1146/2865 = 40% | 897/1963 = 45.70%
PMBurg | 418/6262 = 6.68% | 0/4679 = 0.00% | 418/6262 = 6.68% | 0/4614 = 0.00% | 418/6262 = 6.68% | 32/4548 = 0.70% | 2508/6262 = 40.05% | 32/4548 = 0.70%
Waterval | 162/2422/= 6.69% | 8/1715 = 0.47% | 162/2422/= 6.69% | 86/1762 = 4,88% | 162/2422/= 6.69% | 193/1800 = 10,72% | 972/2422 =40.13% | 682/1800 = 37.89%

## Slide 18
2. SOURCE OF UNDER-ACHIEVEMENT AT CORRECTIONAL CENTRE LEVEL MANAGEMENT
AREA TO POPULATE
Q2 TARGET 2020/21 | QUARTER 2 PERFORMANCE | MANAGEMENT AREAS THAT CONTRIBUTED TOWARDS UNDER-ACHIEVEMENT | CORRECTIONAL CENTRE | REASONS FOR UNDER PERFORMANCE | ROOT CAUSES | ASSOCIATED RISKS
3972/9930 = 40% | 684/7163 = 9.55% | Durban | All Correctional Centres | Target for the quarter not met due to that the limits posed by the lock down. Less spiritual workers were allowed to work according to the risk adjustment strategy | Covid 19 Risk Adjusted Strategy Regulation | Covid 19 Risk Adjusted Strategy Regulation are not relaxed to allow for the provision of fully fledged spiritual care services
1638/4098 = 39.97% | 376/2878 = 13.06% | Empangeni | All Correctional Centres | Target for the quarter not met due to that the limits posed by the lock down. Less spiritual workers were allowed to work according to the risk adjustment strategy | Covid 19 Risk Adjusted Strategy Regulation | Covid 19 Risk Adjusted Strategy Regulation are not relaxed to allow for the provision of fully fledged spiritual care services
960/2407 = 39.88% | 1442/2052 = 70.27% | Glencoe | All Correctional Centres | Target for the quarter not met due to that the limits posed by the lock down. Less spiritual workers were allowed to work according to the risk adjustment strategy | Covid 19 Risk Adjusted Strategy Regulation | Covid 19 Risk Adjusted Strategy Regulation are not relaxed to allow for the provision of fully fledged spiritual care services
840/2106 = 39.89% | 1030/1605 = 64.17% | Kokstad | All Correctional Centres | Target for the quarter not met due to that the limits posed by the lock down. Less spiritual workers were allowed to work according to the risk adjustment strategy | Covid 19 Risk Adjusted Strategy Regulation | Covid 19 Risk Adjusted Strategy Regulation are not relaxed to allow for the provision of fully fledged spiritual care services
PERFORMANCE INDICATOR NOT ACHIEVED:
Percentage of inmates receiving spiritual care services

## Slide 19
2. SOURCE OF UNDER-ACHIEVEMENT AT CORRECTIONAL CENTRE LEVEL MANAGEMENT
AREA TO POPULATE
Q2 TARGET 2020/21 | QUARTER 2 PERFORMANCE | MANAGEMENT AREAS THAT CONTRIBUTED TOWARDS UNDER-ACHIEVEMENT | CORRECTIONAL CENTRE | REASONS FOR UNDER PERFORMANCE | ROOT CAUSES | ASSOCIATED RISKS
1146/2865 = 40% | 897/1963 = 45.70% | Ncome | All Correctional Centres | Target for the quarter not met due to that the limits posed by the lock down. Less spiritual workers were allowed to work according to the risk adjustment strategy | Covid 19 Risk Adjusted Strategy Regulation | Covid 19 Risk Adjusted Strategy Regulation are not relaxed to allow for the provision of fully fledged spiritual care services
2508/6262 = 40.05% | 32/4548 = 0.70% | PMBurg | All Correctional Centres | Target for the quarter not met due to that the limits posed by the lock down. Less spiritual workers were allowed to work according to the risk adjustment strategy | Covid 19 Risk Adjusted Strategy Regulation | Covid 19 Risk Adjusted Strategy Regulation are not relaxed to allow for the provision of fully fledged spiritual care services
972/2422 = 40.13% | 682/1800 = 37.89% | Waterval | All Correctional Centres | Target for the quarter not met due to that the limits posed by the lock down. Less spiritual workers were allowed to work according to the risk adjustment strategy | Covid 19 Risk Adjusted Strategy Regulation | Covid 19 Risk Adjusted Strategy Regulation are not relaxed to allow for the provision of fully fledged spiritual care services
PERFORMANCE INDICATOR NOT ACHIEVED:
Percentage of inmates receiving spiritual care services

## Slide 20
4. PROJECT PLAN TO ADDRESS UNDER PERFORMANCE MANAGEMENT AREA TO POPULATE
MANAGEMENT AREA | CORRECTIONAL CENTRE | ACTIVITY / ACTIVITIES | RESPONSIBILITY | TIME FRAME | PROGRESS
Durban | All Correctional Centres | Continue to involve more offenders in spiritual care services | Area Commissioner and Area Coordinator Dev & Care | October 2020 and ongoing | Offenders are involve in spiritual care services as the Covid 19 Risk Adjusted Strategy Regulation are relaxed.
Empangeni | All Correctional Centres | Continue to involve more offenders in spiritual care services | Area Commissioner and Area Coordinator Dev & Care | October 2020 and ongoing | Offenders are involve in spiritual care services as the Covid 19 Risk Adjusted Strategy Regulation are relaxed.
Glencoe | All Correctional Centres | Continue to involve more offenders in spiritual care services | Area Commissioner and Area Coordinator Dev & Care | October 2020 and ongoing | Offenders are involve in spiritual care services as the Covid 19 Risk Adjusted Strategy Regulation are relaxed.
Kokstad | All Correctional Centres | Continue to involve more offenders in spiritual care services | Area Commissioner and Area Coordinator Dev & Care | October 2020 and ongoing | Offenders are involve in spiritual care services as the Covid 19 Risk Adjusted Strategy Regulation are relaxed.
PLAN TO ADDRESS UNDER PERFORMANCE:
Percentage of inmates receiving spiritual care services

## Slide 21
4. PROJECT PLAN TO ADDRESS UNDER PERFORMANCE MANAGEMENT AREA TO POPULATE
MANAGEMENT AREA | CORRECTIONAL CENTRE | ACTIVITY / ACTIVITIES | RESPONSIBILITY | TIME FRAME | PROGRESS
Ncome | All Correctional Centres | Continue to involve more offenders in spiritual care services | Area Commissioner and Area Coordinator Dev & Care | October 2020 and ongoing | Offenders are involve in spiritual care services as the Covid 19 Risk Adjusted Strategy Regulation are relaxed.
PMBurg | All Correctional Centres | Continue to involve more offenders in spiritual care services | Area Commissioner and Area Coordinator Dev & Care | October 2020 and ongoing | Offenders are involve in spiritual care services as the Covid 19 Risk Adjusted Strategy Regulation are relaxed.
Waterval | All Correctional Centres | Continue to involve more offenders in spiritual care services | Area Commissioner and Area Coordinator Dev & Care | October 2020 and ongoing | Offenders are involve in spiritual care services as the Covid 19 Risk Adjusted Strategy Regulation are relaxed.
PLAN TO ADDRESS UNDER PERFORMANCE:
Percentage of inmates receiving spiritual care services

## Slide 22
PERFORMANCE INDICATOR NOT ACHIEVED:
Percentage of inmates receiving psychological care services
1. REGIONAL TARGET VERSUS PERFORMANCE FOR 2nd QUARTER (2020/2021)
2. SOURCE OF UNDER-ACHIEVEMENT AT MANAGEMENT AREA LEVEL
REGION | JULY 2020 TARGET | JULY PERFORMANCE | AUGUST 2020 TARGET | AUGUST PERFORMANCE | SEPTEMBER 2020 TARGET | SEPTEMBER PERFORMANCE | Q2 TARGET: 2020-2021 | PERFORMANCE
Kwa Zulu Natal | 390/30090= 1.30% | 253/22164 = 1.14% | 390/30090= 1.30% | 293/218531 =1.34% | 390/30090= 1.30% | 346/22009 = 1.57% | 10% | 1649/22009 = 7.49%
MANAGEMENT AREA | JULY 2020 TARGET | JULY PERFORMANCE | AUGUST 2020 TARGET | AUGUST PERFORMANCE | SEPTEMBER 2020 TARGET | SEPTEMBER PERFORMANCE | Q2 TARGET: 2020-2021 | PERFORMANCE
Durban | 120/9930 = 1.21% | 34/7604 =0.45% | 120/9930 = 1.21% | 29/7389 = 0.39% | 120/9930 = 1.21% | 32/7163 = 0.45% | 720/9930 = 7.25% | 235/7163 = 3.28%
Empangeni | 60/4098 = 1.46% | 38/2875 = 1.32% | 60/4098 = 1.46% | 27/2895 = 0.93% | 60/4098 = 1.46% | 25/2878 = 0.87% | 360/4098 = 8.78% | 244/2878 = 8.48%
Glencoe | 0/2407 = 0.00% | 0/1649 = 0.00% | 0/2407 = 0.00% | 0/1620 = 0.00% | 0/2407 = 0.00% | 0/2052 = 0.00% | 0/2407 = 0.00% | 0/2052 = 0.00%
Kokstad | 60/2106 = 2.85% | 66/1537 = 4.29% | 60/2106 = 2.85% | 75/1534 = 4.89% | 60/2106 = 2.85% | 55/1605 = 3.43% | 360/2106 = 17.09% | 355/1605 = 22.12%

## Slide 23
PERFORMANCE INDICATOR NOT ACHIEVED:
Percentage of inmates receiving psychological care services
2. SOURCE OF UNDER-ACHIEVEMENT AT MANAGEMENT AREA LEVEL (CONT…)
MANAGEMENT AREA | JULY 2020 TARGET | JULY PERFORMANCE | AUGUST 2020 TARGET | AUGUST PERFORMANCE | SEPTEMBER 2020 TARGET | SEPTEMBER PERFORMANCE | Q2 TARGET: 2020-2021 | PERFORMANCE
Ncome | 30/2865 = 1.05% | 30/2105 = 1.43% | 30/2865 = 1.05% | 34/2045 = 1.66% | 30/2865 = 1.05% | 48/1963 = 2.45% | 180/2865 = 6.28% | 178/1963 = 9.07%
PMBurg | 90/6262 = 1.44% | 48/4679 = 1.03% | 90/6262 = 1.44% | 82/4614 = 1.78% | 90/6262 = 1.44% | 135/4548 = 2.97% | 540/6262 = 8.62% | 445/4548 = 9.78%
Waterval | 30/2422 = 1.24% | 37/1715 = 2.16% | 30/2422 = 1.24% | 46/1762 = 2.61% | 30/2422 = 1.24% | 51/1800 = 2.83% | 180/2422 = 7.43% | 192/1800 = 10.67%

## Slide 24
2. SOURCE OF UNDER-ACHIEVEMENT AT CORRECTIONAL CENTRE LEVEL MANAGEMENT
AREA TO POPULATE
Q2 TARGET 2020/21 | QUARTER 2 PERFORMANCE | MANAGEMENT AREAS THAT CONTRIBUTED TOWARDS UNDER-ACHIEVEMENT | CORRECTIONAL CENTRE | REASONS FOR UNDER PERFORMANCE | ROOT CAUSES | ASSOCIATED RISKS
720/9930 = 7.25% | 235/7163 = 3.28% | Durban | All Correctional Centres | Target for the quarter not met due to that limitation of the risk adjustment strategy. Size of the groups were limited to 8- 10 depending on the size of the venue | Covid 19 Risk Adjusted Strategy Regulation | Covid 19 Risk Adjusted Strategy Regulation are not relaxed to allow for the provision of fully fledged psychological care services
360/4098 = 8.78% | 244/2878 = 8.48% | Empangeni | All Correctional Centres | arget for the quarter not met due to that limitation of the risk addjustment strategy. Size of the groups were limited to 8- 10 depending on the size of the venue | Covid 19 Risk Adjusted Strategy Regulation | Covid 19 Risk Adjusted Strategy Regulation are not relaxed to allow for the provision of fully fledged psychological care services
0/2407 = 0.00% | 0/2052 = 0.00% | Glencoe | All Correctional Centres | arget for the quarter not met due to that limitation of the risk addjustment strategy. Size of the groups were limited to 8- 10 depending on the size of the venue | Covid 19 Risk Adjusted Strategy Regulation | Covid 19 Risk Adjusted Strategy Regulation are not relaxed to allow for the provision of fully fledged psychological care services
360/2106 = 17.09% | 355/1605 = 22.12% | Kokstad | All Correctional Centres | Target for the quarter not met due to that limitation of the risk adjustment strategy. Size of the groups were limited to 8- 10 depending on the size of the venue | Covid 19 Risk Adjusted Strategy Regulation | Covid 19 Risk Adjusted Strategy Regulation are not relaxed to allow for the provision of fully fledged psychological care services
PERFORMANCE INDICATOR NOT ACHIEVED:
Percentage of inmates receiving psychological care services

## Slide 25
2. SOURCE OF UNDER-ACHIEVEMENT AT CORRECTIONAL CENTRE LEVEL MANAGEMENT
AREA TO POPULATE
Q2 TARGET 2020/21 | QUARTER 2 PERFORMANCE | MANAGEMENT AREAS THAT CONTRIBUTED TOWARDS UNDER-ACHIEVEMENT | CORRECTIONAL CENTRE | REASONS FOR UNDER PERFORMANCE | ROOT CAUSES | ASSOCIATED RISKS
180/2865 = 6.28% | 178/1963 = 9.07% | Ncome | All Correctional Centres | arget for the quarter not met due to that limitation of the risk addjustment strategy. Size of the groups were limited to 8- 10 depending on the size of the venue | Covid 19 Risk Adjusted Strategy Regulation | Covid 19 Risk Adjusted Strategy Regulation are not relaxed to allow for the provision of fully fledged psychological care services
540/6262 = 8.62% | 445/4548 = 9.78% | PMBurg | All Correctional Centres | arget for the quarter not met due to that limitation of the risk addjustment strategy. Size of the groups were limited to 8- 10 depending on the size of the venue | Covid 19 Risk Adjusted Strategy Regulation | Covid 19 Risk Adjusted Strategy Regulation are not relaxed to allow for the provision of fully fledged psychological care services
180/2422 = 7.43% | 192/1800 = 10.67% | Waterval | All Correctional Centres | Target for the quarter not met due to that limitation of the risk adjustment strategy. Size of the groups were limited to 8- 10 depending on the size of the venue | Covid 19 Risk Adjusted Strategy Regulation | Covid 19 Risk Adjusted Strategy Regulation are not relaxed to allow for the provision of fully fledged psychological care services
PERFORMANCE INDICATOR NOT ACHIEVED:
Percentage of inmates receiving psychological care services

## Slide 26
4. PROJECT PLAN TO ADDRESS UNDER PERFORMANCE MANAGEMENT AREA TO POPULATE
MANAGEMENT AREA | CORRECTIONAL CENTRE | ACTIVITY / ACTIVITIES | RESPONSIBILITY | TIME FRAME | PROGRESS
Durban | All Correctional Centres | Continue to involve more offenders in psychological care services | Area Commissioner and Area Coordinator Dev & Care | October 2020 and ongoing | Offenders are involve in psychological care services as the Covid 19 Risk Adjusted Strategy Regulation are not relaxed.
Empangeni | All Correctional Centres | Continue to involve more offenders in psychological care services | Area Commissioner and Area Coordinator Dev & Care | October 2020 and ongoing | Offenders are involve in psychological care services as the Covid 19 Risk Adjusted Strategy Regulation are not relaxed.
Glencoe | All Correctional Centres | Continue to involve more offenders in psychological care services | Area Commissioner and Area Coordinator Dev & Care | October 2020 and ongoing | Offenders are involve in psychological care services as the Covid 19 Risk Adjusted Strategy Regulation are not relaxed.
Kokstad | All Correctional Centres | Continue to involve more offenders in psychological care services | Area Commissioner and Area Coordinator Dev & Care | October 2020 and ongoing | Offenders are involve in psychological care services as the Covid 19 Risk Adjusted Strategy Regulation are not relaxed.
PLAN TO ADDRESS UNDER PERFORMANCE:
Percentage of inmates receiving psychological care services

## Slide 27
4. PROJECT PLAN TO ADDRESS UNDER PERFORMANCE MANAGEMENT AREA TO POPULATE
MANAGEMENT AREA | CORRECTIONAL CENTRE | ACTIVITY / ACTIVITIES | RESPONSIBILITY | TIME FRAME | PROGRESS
Ncome | All Correctional Centres | Continue to involve more offenders in psychological care services | Area Commissioner and Area Coordinator Dev & Care | October 2020 and ongoing | Offenders are involve in psychological care services as the Covid 19 Risk Adjusted Strategy Regulation are not relaxed.
PMBurg | All Correctional Centres | Continue to involve more offenders in psychological care services | Area Commissioner and Area Coordinator Dev & Care | October 2020 and ongoing | Offenders are involve in psychological care services as the Covid 19 Risk Adjusted Strategy Regulation are not relaxed.
Waterval | All Correctional Centres | Continue to involve more offenders in psychological care services | Area Commissioner and Area Coordinator Dev & Care | October 2020 and ongoing | Offenders are involve in psychological care services as the Covid 19 Risk Adjusted Strategy Regulation are not relaxed.
PLAN TO ADDRESS UNDER PERFORMANCE:
Percentage of inmates receiving psychological care services

## Slide 28
PROGRAMME
CARE

## Slide 29
PERFORMANCE INDICATOR NOT ACHIEVED:
Percentage of identified inmates who have tested for Corona virus Disease 2019 (COVID-19)
1. REGIONAL TARGET VERSUS PERFORMANCE FOR 2nd QUARTER (2020/2021)
2. SOURCE OF UNDER-ACHIEVEMENT AT MANAGEMENT AREA LEVEL
REGION | JULY 2020 TARGET | JULY PERFORMANCE | AUGUST 2020 TARGET | AUGUST PERFORMANCE | SEPTEMBER 2020 TARGET | SEPTEMBER PERFORMANCE | Q2 TARGET: 2020-2021 | PERFORMANCE
Kwa Zulu Natal | 0/0 = 0.00 % | 82/94 = 87.23 % | 0/0 = 0.00 % | 149/498 = 29.92 % | 0/0 = 0.00 % | 6/8 = 75 % | 0/0 = 0.00 % | 373/736 = 50.68 %
MANAGEMENT AREA | JULY 2020 TARGET | JULY PERFORMANCE | AUGUST 2020 TARGET | AUGUST PERFORMANCE | SEPTEMBER 2020 TARGET | SEPTEMBER PERFORMANCE | Q2 TARGET: 2020-2021 | PERFORMANCE
Durban | 0/0 = 0.00 % | 0/12 = 0.00 % | 0/0 = 0.00 % | 0/7 = 0.00 % | 0/0 = 0.00 % | 0/2 = 0.00 % | 0/0 = 0.00 % | 120/141 = 85.11 %
Empangeni | 0/0 = 0.00 % | 9/9 = 100 % | 0/0 = 0.00 % | 75.252 = 29.76 % | 0/0 = 0.00 % | 0/0 = 0.00 % | 0/0 = 0.00 % | 87/264 = 32.95%
Glencoe | 0/0 = 0.00 % | 9/9 = 100 % | 0/0 = 0.00 % | 32/32 = 100 % | 0/0 = 0.00 % | 4/4 = 100% | 0/0 = 0.00 % | 45/45 = 100%
Kokstad | 0/0 = 0.00 % | 8/8 = 100 % | 0/0 = 0.00 % | 13/13 = 100% | 0/0 = 0.00 % | 1/1 = 100% | 0/0 = 0.00 % | 22/22 = 100%

## Slide 30
PERFORMANCE INDICATOR NOT ACHIEVED:
Percentage of identified inmates who have tested for Corona virus Disease 2019 (COVID-19)
2. SOURCE OF UNDER-ACHIEVEMENT AT MANAGEMENT AREA LEVEL (CONT…)
MANAGEMENT AREA | JULY 2020 TARGET | JULY PERFORMANCE | AUGUST 2020 TARGET | AUGUST PERFORMANCE | SEPTEMBER 2020 TARGET | SEPTEMBER PERFORMANCE | Q2 TARGET: 2020-2021 | PERFORMANCE
Ncome | 0/0 = 0.00 % | 1/1 = 100 % | 0/0 = 0.00 % | 35/35 = 100 % | 0/0 = 0.00 % | 0 / 0 = 100 % | 0/0 = 0.00 % | 36/36 = 100 %
PMBurg | 0/0 = 0.00 % | 55/55 = 100 % | 0/0 = 0.00 % | 39/180 = 21.67 % | 0/0 = 0.00 % | 1 / 1 = 100 % | 0/0 = 0.00 % | 95/236 = 40.25 %
Waterval | 0/0 = 0.00 % | 0/0 0.00 % | 0/0 = 0.00 % | 5 / 5 = 100 % | 0/0 = 0.00 % | 0 / 0 = 0.00 % | 0/0 = 0.00 % | 5/5 = 100 %

## Slide 31
2. SOURCE OF UNDER-ACHIEVEMENT AT CORRECTIONAL CENTRE LEVEL MANAGEMENT
AREA TO POPULATE
Q2 TARGET 2020/21 | QUARTER 2 PERFORMANCE | MANAGEMENT AREAS THAT CONTRIBUTED TOWARDS UNDER-ACHIEVEMENT | CORRECTIONAL CENTRE | REASONS FOR UNDER PERFORMANCE | ROOT CAUSES | ASSOCIATED RISKS
0/0 = 0.00 % | 120/141 = 85.11 % | Durban | All Correctional Centres | Target for the quarter not met due to the fact that identified inmates did not meet the set KZN DoH criteria for testing Covid -19 | Covid 19 Risk Adjusted Strategy Regulation | The surge of infection within Correctional facilities causing more complications Human capital and other Resources will be strained Inadequate service provision and service delivery.
0/0 = 0.00 % | 87/264 = 32.95% | Empangeni | All Correctional Centres | Target for the quarter not met due to the fact that identified inmates did not meet the set KZN DoH criteria for testing Covid -19 | Covid 19 Risk Adjusted Strategy Regulation | The surge of infection within Correctional facilities causing more complications Human capital and other Resources will be strained Inadequate service provision and service delivery
0/0 = 0.00 % | 45/45 = 100% | Glencoe | All Correctional Centres | Target for the quarter not met due to the fact that identified inmates did not meet the set KZN DoH criteria for testing Covid -19 | Covid 19 Risk Adjusted Strategy Regulation | The surge of infection within Correctional facilities causing more complications Human capital and other Resources will be strained Inadequate service provision and service delivery
0/0 = 0.00 % | 22/22 = 100% | Kokstad | All Correctional Centres | Target for the quarter not met due to the fact that identified inmates did not meet the set KZN DoH criteria for testing Covid -19 | Covid 19 Risk Adjusted Strategy Regulation | The surge of infection within Correctional facilities causing more complications Human capital and other Resources will be strained Inadequate service provision and service delivery
PERFORMANCE INDICATOR NOT ACHIEVED:
Percentage of identified inmates who have tested for Corona virus Disease (Covid – 19)

## Slide 32
2. SOURCE OF UNDER-ACHIEVEMENT AT CORRECTIONAL CENTRE LEVEL MANAGEMENT AREA TO
POPULATE
Q2 TARGET 2020/21 | QUARTER 2 PERFORMANCE | MANAGEMENT AREAS THAT CONTRIBUTED TOWARDS UNDER-ACHIEVEMENT | CORRECTIONAL CENTRE | REASONS FOR UNDER PERFORMANCE | ROOT CAUSES | ASSOCIATED RISKS
0/0 = 0.00 % | 36/36 = 100 % | Ncome | All Correctional Centres | Target for the quarter not met due to the fact that identified inmates did not meet the set KZN DoH criteria for testing Covid -19 | Covid 19 Risk Adjusted Strategy Regulation | The surge of infection within Correctional facilities causing more complications Human capital and other Resources will be strained Inadequate service provision and service delivery
0/0 = 0.00 % | 95/236 = 40.25 % | PMBurg | All Correctional Centres | Target for the quarter not met due to the fact that identified inmates did not meet the set KZN DoH criteria for testing Covid -19 | Covid 19 Risk Adjusted Strategy Regulation | The surge of infection within Correctional facilities causing more complications Human capital and other Resources will be strained Inadequate service provision and service delivery
0/0 = 0.00 % | 5/5 = 100 % | Waterval | All Correctional Centres | Target for the quarter not met due to the fact that identified inmates did not meet the set KZN DoH criteria for testing Covid -19 | Covid 19 Risk Adjusted Strategy Regulation | The surge of infection within Correctional facilities causing more complications Human capital and other Resources will be strained Inadequate service provision and service delivery
PERFORMANCE INDICATOR NOT ACHIEVED:
Percentage of identified inmates who have tested for Corona virus Disease 2019 (COVID-19)

## Slide 33
4. PROJECT PLAN TO ADDRESS UNDER PERFORMANCE MANAGEMENT AREA TO POPULATE
MANAGEMENT AREA | CORRECTIONAL CENTRE | ACTIVITY / ACTIVITIES | RESPONSIBILITY | TIME FRAME | PROGRESS
Durban | All Correctional Centres | Continue to conduct awareness raising sessions for inmates and to identify suspected inmates for testing | Area Commissioner and Area Coordinator Dev & Care, and Head of Centre | October 2020 and ongoing | Awareness raising is continued, inmates are identified and tested in line with the DoH Covid -19 protocols and the departmental Strategic Plan for Covid - 19
Empangeni | All Correctional Centres | Continue to conduct awareness raising sessions for inmates and to identify suspected inmates for testing | Area Commissioner and Area Coordinator Dev & Care, and Head of Centre | October 2020 and ongoing | Awareness raising is continued, inmates are identified and tested in line with the DoH Covid -19 protocols and the departmental Strategic Plan for Covid - 19
Glencoe | All Correctional Centres | Continue to conduct awareness raising sessions for inmates and to identify suspected inmates for testing | Area Commissioner and Area Coordinator Dev & Care, and Head of Centre | October 2020 and ongoing | Awareness raising is continued, inmates are identified and tested in line with the DoH Covid -19 protocols and the departmental Strategic Plan for Covid - 19
Kokstad | All Correctional Centres | Continue to conduct awareness raising sessions for inmates and to identify suspected inmates for testing | Area Commissioner and Area Coordinator Dev & Care, and Head of Centre | October 2020 and ongoing | Awareness raising is continued, inmates are identified and tested in line with the DoH Covid -19 protocols and the departmental Strategic Plan for Covid - 19
PLAN TO ADDRESS UNDER PERFORMANCE:
Percentage of identified inmates who have tested for Corona virus Disease 2019 (COVID-19)

## Slide 34
4. PROJECT PLAN TO ADDRESS UNDER PERFORMANCE MANAGEMENT AREA TO POPULATE
MANAGEMENT AREA | CORRECTIONAL CENTRE | ACTIVITY / ACTIVITIES | RESPONSIBILITY | TIME FRAME | PROGRESS
Ncome | All Correctional Centres | Continue to conduct awareness raising sessions for inmates and to identify suspected inmates for testing | Area Commissioner and Area Coordinator Dev & Care, and Head of Centre | October 2020 and ongoing | Awareness raising is continued, inmates are identified and tested in line with the DoH Covid -19 protocols and the departmental Strategic Plan for Covid - 19
PMBurg | All Correctional Centres | Continue to conduct awareness raising sessions for inmates and to identify suspected inmates for testing | Area Commissioner and Area Coordinator Dev & Care, and Head of Centre | October 2020 and ongoing | Awareness raising is continued, inmates are identified and tested in line with the DoH Covid -19 protocols and the departmental Strategic Plan for Covid - 19
Waterval | All Correctional Centres | Continue to conduct awareness raising sessions for inmates and to identify suspected inmates for testing | Area Commissioner and Area Coordinator Dev & Care, and Head of Centre | October 2020 and ongoing | Awareness raising is continued, inmates are identified and tested in line with the DoH Covid -19 protocols and the departmental Strategic Plan for Covid - 19
PLAN TO ADDRESS UNDER PERFORMANCE:
Percentage of identified inmates who have tested for Corona virus Disease 2019 (COVID-19)

## Slide 35
PROGRAMME 5
SOCIAL REINTEGATION

## Slide 36
PERFORMANCE INDICATOR NOT ACHIEVED:
'Percentage increase of victims participating in Restorative Justice Programme
1. REGIONAL TARGET VERSUS PERFORMANCE FOR 2nd QUARTER (2020/2021)
2. SOURCE OF UNDER-ACHIEVEMENT AT MANAGEMENT AREA LEVEL
REGION | JULY 2020 TARGET | JULY PERFORMANCE | AUGUST 2020 TARGET | AUGUST PERFORMANCE | SEPTEMBER 2020 TARGET | SEPTEMBER PERFORMANCE | Q2 TARGET: 2020-2021 | PERFORMANCE
Kwa Zulu Natal | 298 | 20 | 298 | 25 | 298 | 249 | 7% | (-1 327/1 621)= -81.86%
MANAGEMENT AREA | JULY 2020 TARGET | JULY PERFORMANCE | AUGUST 2020 TARGET | AUGUST PERFORMANCE | SEPTEMBER 2020 TARGET | SEPTEMBER PERFORMANCE | Q2 TARGET: 2020-2021 | PERFORMANCE
Durban | 55 | 0 | 55 | 1 | 55 | 27 | 330 | 28
Empangeni | 82 | 13 | 82 | 17 | 82 | 28 | 491 | 75
Glencoe | 20 | 0 | 20 | 0 | 20 | 1 | 120 | 1
Kokstad | 64 | 0 | 64 | 0 | 64 | 46 | 384 | 46

## Slide 37
PERFORMANCE INDICATOR NOT ACHIEVED:
'Percentage increase of victims participating in Restorative Justice Programme
2. SOURCE OF UNDER-ACHIEVEMENT AT MANAGEMENT AREA LEVEL (CONT…)
MANAGEMENT AREA | JULY 2020 TARGET | JULY PERFORMANCE | AUGUST 2020 TARGET | AUGUST PERFORMANCE | SEPTEMBER 2020 TARGET | SEPTEMBER PERFORMANCE | Q2 TARGET: 2020-2021 | PERFORMANCE
Ncome | 32 | 0 | 32 | 0 | 32 | 16 | 192 | 16
PMBurg | 23 | 7 | 23 | 7 | 23 | 104 | 138 | 125
Waterval | 22 | 0 | 22 | 0 | 22 | 27 | 132 | 27

## Slide 38
2. SOURCE OF UNDER-ACHIEVEMENT AT CORRECTIONAL CENTRE LEVEL MANAGEMENT
AREA TO POPULATE
Q2 TARGET 2020/21 | QUARTER 2 PERFORMANCE | MANAGEMENT AREAS THAT CONTRIBUTED TOWARDS UNDER-ACHIEVEMENT | CORRECTIONAL CENTRE | REASONS FOR UNDER PERFORMANCE | ROOT CAUSES | ASSOCIATED RISKS
330/0 = 0.00% | 28/0 = 0.00% | Durban | All Correctional Centres | Restorative Justice Programme suspended due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Suspension of Restorative Justice Programme due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Goal of effectively and efficiently reintegrating offenders in to communities not realised and lack of meaningful involvement of victims in retorative Justice Programme
491/0 = 0.00% | 75/0 = 0.00% | Empangeni | All Correctional Centres | Restorative Justice Programme suspended due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Suspension of Restorative Justice Programme due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Goal of effectively and efficiently reintegrating offenders in to communities not realized and lack of meaningful involvement of victims in restorative Justice Programme
120/0 = 0.00% | 1/0= 0.00% | Glencoe | All Correctional Centres | Restorative Justice Programme suspended due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Suspension of Restorative Justice Programme due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Goal of effectively and efficiently reintegrating offenders in to communities not realized and lack of meaningful involvement of victims in restorative Justice Programme
384/0 = 0.00% | 46/0 = 0.00% Denominator to be included | Kokstad | All Correctional Centres | Restorative Justice Programme suspended due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Suspension of Restorative Justice Programme due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Goal of effectively and efficiently reintegrating offenders in to communities not realized and lack of meaningful involvement of victims in restorative Justice Programme
PERFORMANCE INDICATOR NOT ACHIEVED:
'Percentage increase of victims participating in Restorative Justice Programme

## Slide 39
2. SOURCE OF UNDER-ACHIEVEMENT AT CORRECTIONAL CENTRE LEVEL MANAGEMENT
AREA TO POPULATE
Q2 TARGET 2020/21 | QUARTER 2 PERFORMANCE | MANAGEMENT AREAS THAT CONTRIBUTED TOWARDS UNDER-ACHIEVEMENT | CORRECTIONAL CENTRE | REASONS FOR UNDER PERFORMANCE | ROOT CAUSES | ASSOCIATED RISKS
192/0 = 0.00% | 16/0 = 0.00% | Ncome | All Correctional Centres | Restorative Justice Programme suspended due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Suspension of Restorative Justice Programme due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Goal of effectively and efficiently reintegrating offenders in to communities not realized and lack of meaningful involvement of victims in restorative Justice Programme
138/0 = 0.00% | 125/0 =0.00% | PMBurg | All Correctional Centres | Restorative Justice Programme suspended due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Suspension of Restorative Justice Programme due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Goal of effectively and efficiently reintegrating offenders in to communities not realized and lack of meaningful involvement of victims in restorative Justice Programme
132/0 = 0.00% | 27/0 = 0.00% | Waterval | All Correctional Centres | Restorative Justice Programme suspended due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Suspension of Restorative Justice Programme due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Goal of effectively and efficiently reintegrating offenders in to communities not realized and lack of meaningful involvement of victims in restorative Justice Programme
PERFORMANCE INDICATOR NOT ACHIEVED:
'Percentage increase of victims participating in Restorative Justice Programme

## Slide 40
4. PROJECT PLAN TO ADDRESS UNDER PERFORMANCE MANAGEMENT AREA TO POPULATE
MANAGEMENT AREA | CORRECTIONAL CENTRE | ACTIVITY / ACTIVITIES | RESPONSIBILITY | TIME FRAME | PROGRESS
Durban | All Correctional Centres | Restorative Justices Programme activities to commence according to Covid 19 Risk Adjustment Strategy. | Area Commissioner and Area Coordinator Corrections | October 2020 and ongoing | Covid 19 Risk Adjusted Strategy Regulation are not relaxed to allow for fully fledged restorative justice activities
Empangeni | All Correctional Centres | Restorative Justices Programme activities to commence according to Covid 19 Risk Adjustment Strategy. | Area Commissioner and Area Coordinator Corrections | October 2020 and ongoing | Covid 19 Risk Adjusted Strategy Regulation are not relaxed to allow for fully fledged restorative justice activities
Glencoe | All Correctional Centres | Restorative Justices Programme activities to commence according to Covid 19 Risk Adjustment Strategy. | Area Commissioner and Area Coordinator Corrections | October 2020 and ongoing | Covid 19 Risk Adjusted Strategy Regulation are not relaxed to allow for fully fledged restorative justice activities
Kokstad | All Correctional Centres | Restorative Justices Programme activities to commence according to Covid 19 Risk Adjustment Strategy. | Area Commissioner and Area Coordinator Corrections | October 2020 and ongoing | Covid 19 Risk Adjusted Strategy Regulation are not relaxed to allow for fully fledged restorative justice activities
PLAN TO ADDRESS UNDER PERFORMANCE:
'Percentage increase of victims participating in Restorative Justice Programme

## Slide 41
4. PROJECT PLAN TO ADDRESS UNDER PERFORMANCE MANAGEMENT AREA TO POPULATE
MANAGEMENT AREA | CORRECTIONAL CENTRE | ACTIVITY / ACTIVITIES | RESPONSIBILITY | TIME FRAME | PROGRESS
Ncome | All centres | Restorative Justices Programme activities to commence according to Covid 19 Risk Adjustment Strategy. | Area Commissioner and Area Coordinator Corrections | October 2020 and ongoing | Covid 19 Risk Adjusted Strategy Regulation are not relaxed to allow for fully fledged restorative justice activities . VOD resuscitated during lockdown alert level 1 marketing of VOD to Imbizos and local community radio stations
PMBurg | All centres | Restorative Justices Programme activities to commence according to Covid 19 Risk Adjustment Strategy. | Area Commissioner and Area Coordinator Corrections | October 2020 and ongoing | Covid 19 Risk Adjusted Strategy Regulation are not relaxed to allow for fully fledged restorative justice activities . VOD resuscitated during lockdown alert level 1 marketing of VOD to Imbizos and local community radio stations
Waterval | All centres | Restorative Justices Programme activities to commence according to Covid 19 Risk Adjustment Strategy. | Area Commissioner and Area Coordinator Corrections | October 2020 and ongoing | Covid 19 Risk Adjusted Strategy Regulation are not relaxed to allow for fully fledged restorative justice activities . VOD resuscitated during lockdown alert level 1 marketing of VOD to Imbizos and local community radio stations
PLAN TO ADDRESS UNDER PERFORMANCE:
'Percentage increase of victims participating in Restorative Justice Programme

## Slide 42
PERFORMANCE INDICATOR NOT ACHIEVED:
Percentage increase of offenders, parolees and probationers participating in Restorative Justice Programme
1. REGIONAL TARGET VERSUS PERFORMANCE FOR 2nd QUARTER (2020/2021)
2. SOURCE OF UNDER-ACHIEVEMENT AT MANAGEMENT AREA LEVEL
REGION | JULY 2020 TARGET | JULY PERFORMANCE | AUGUST 2020 TARGET | AUGUST PERFORMANCE | SEPTEMBER 2020 TARGET | SEPTEMBER PERFORMANCE | Q2 TARGET: 2020-2021 | PERFORMANCE
Kwa Zulu Natal | 68 | 12 | 68 | 20 | 68 | 48 | 3% | ( -326/410)= -79.51%
MANAGEMENT AREA | JULY 2020 TARGET | JULY PERFORMANCE | AUGUST 2020 TARGET | AUGUST PERFORMANCE | SEPTEMBER 2020 TARGET | SEPTEMBER PERFORMANCE | Q2 TARGET: 2020-2021 | PERFORMANCE
Durban | 13 | 0 | 13 | 1 | 13 | 6 | 39 | 7
Empangeni | 19 | 5 | 19 | 11 | 19 | 10 | 57 | 30
Glencoe | 7 | 0 | 7 | 1 | 7 | 1 | 21 | 2
Kokstad | 15 | 0 | 15 | 0 | 15 | 7 | 45 | 7

## Slide 43
PERFORMANCE INDICATOR NOT ACHIEVED:
Percentage increase of offenders, parolees and probationers participating in Restorative Justice Programme
2. SOURCE OF UNDER-ACHIEVEMENT AT MANAGEMENT AREA LEVEL (CONT…)
MANAGEMENT AREA | JULY 2020 TARGET | JULY PERFORMANCE | AUGUST 2020 TARGET | AUGUST PERFORMANCE | SEPTEMBER 2020 TARGET | SEPTEMBER PERFORMANCE | Q2 TARGET: 2020-2021 | PERFORMANCE
Ncome | 5 | 0 | 5 | 0 | 5 | 4 | 15 | 4
PMBurg | 6 | 7 | 6 | 7 | 6 | 13 | 18 | 27
Waterval | 3 | 0 | 3 | 0 | 3 | 7 | 9 | 7

## Slide 44
2. SOURCE OF UNDER-ACHIEVEMENT AT CORRECTIONAL CENTRE LEVEL MANAGEMENT AREA
TO POPULATE
Q2 TARGET 2020/21 | QUARTER 2 PERFORMANCE | MANAGEMENT AREAS THAT CONTRIBUTED TOWARDS UNDER-ACHIEVEMENT | CORRECTIONAL CENTRE | REASONS FOR UNDER PERFORMANCE | ROOT CAUSES | ASSOCIATED RISKS
39/0 = 0.00% | 7/0 = 0.00% | Durban | All Correctional Centres | Restorative Justice Programme suspended due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Suspension of Restorative Justice Programme due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Goal of effectively and efficiently reintegrating offenders in to communities not realized and lack of meaningful involvement of victims in restorative Justice Programme
57/0 = 0.00% | 30/0 = 0.00% | Empangeni | All Correctional Centres | Restorative Justice Programme suspended due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Suspension of Restorative Justice Programme due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Goal of effectively and efficiently reintegrating offenders in to communities not realized and lack of meaningful involvement of victims in restorative Justice Programme
21/0 = 0.00% | 2/0 = 0.00% | Glencoe | All Correctional Centres | Restorative Justice Programme suspended due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Suspension of Restorative Justice Programme due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Goal of effectively and efficiently reintegrating offenders in to communities not realized and lack of meaningful involvement of victims in restorative Justice Programme
45/0 = 0.00% | 7/0 = 0.00% Denominator to be included | Kokstad | All Correctional Centres | Restorative Justice Programme suspended due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Suspension of Restorative Justice Programme due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Goal of effectively and efficiently reintegrating offenders in to communities not realized and lack of meaningful involvement of victims in restorative Justice Programme
PERFORMANCE INDICATOR NOT ACHIEVED:
Percentage increase of offenders, parolees and probationers participating in Restorative Justice Programme

## Slide 45
2. SOURCE OF UNDER-ACHIEVEMENT AT CORRECTIONAL CENTRE LEVEL MANAGEMENT AREA
TO POPULATE
Q2 TARGET 2020/21 | QUARTER 2 PERFORMANCE | MANAGEMENT AREAS THAT CONTRIBUTED TOWARDS UNDER-ACHIEVEMENT | CORRECTIONAL CENTRE | REASONS FOR UNDER PERFORMANCE | ROOT CAUSES | ASSOCIATED RISKS
15/0 = 0.00% | 4/0 = 0.00% | Ncome | All Correctional Centres | Restorative Justice Programme suspended due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Suspension of Restorative Justice Programme due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Goal of effectively and efficiently reintegrating offenders in to communities not realized and lack of meaningful involvement of victims in restorative Justice Programme
18/0 = 0.00% | 27/0 = 0.00% | Pietermaritzburg | All Correctional Centres | Restorative Justice Programme suspended due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Suspension of Restorative Justice Programme due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Goal of effectively and efficiently reintegrating offenders in to communities not realized and lack of meaningful involvement of victims in restorative Justice Programme
9/0 = 0.00% | 7/0 = 0.00% | Waterval | All Correctional Centres | Restorative Justice Programme suspended due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Suspension of Restorative Justice Programme due to Covid 19 Risk Adjusted Strategy (Suspension of visits to Correctional Centres | Goal of effectively and efficiently reintegrating offenders in to communities not realized and lack of meaningful involvement of victims in restorative Justice Programme
PERFORMANCE INDICATOR NOT ACHIEVED:
Percentage increase of offenders, parolees and probationers participating in Restorative Justice Programme

## Slide 46
4. PROJECT PLAN TO ADDRESS UNDER PERFORMANCE MANAGEMENT AREA TO POPULATE
MANAGEMENT AREA | CORRECTIONAL CENTRE | ACTIVITY / ACTIVITIES | RESPONSIBILITY | TIME FRAME | PROGRESS
Durban | All Correctional Centres | Formulate VOD Forums in each centre Develop a tracing unit within the management area Encourage offenders to participate in VOD | Area Commissioner and Area Coordinator Corrections | October 2020 and ongoing | Formulate d VOD Forums in each centre Developed a tracing unit within the management area Encouraged offenders to participate in VOD
Empangeni | All Correctional Centres | Formulate VOD Forums in each centre Develop a tracing unit within the management area Encourage offenders to participate in VOD | Area Commissioner and Area Coordinator Corrections | October 2020 and ongoing | Formulate d VOD Forums in each centre Developed a tracing unit within the management area Encouraged offenders to participate in VOD
Glencoe | All Correctional Centres | Formulate VOD Forums in each centre Develop a tracing unit within the management area Encourage offenders to participate in VOD | Area Commissioner and Area Coordinator Corrections | October 2020 and ongoing | Formulate d VOD Forums in each centre Developed a tracing unit within the management area Encouraged offenders to participate in VOD
Kokstad | All Correctional Centres | Formulate VOD Forums in each centre Develop a tracing unit within the management area Encourage offenders to participate in VOD | Area Commissioner and Area Coordinator Corrections | October 2020 and ongoing | Formulate d VOD Forums in each centre Developed a tracing unit within the management area Encouraged offenders to participate in VOD
PLAN TO ADDRESS UNDER PERFORMANCE:
Percentage increase of offenders, parolees and probationers participating in Restorative Justice Programme

## Slide 47
4. PROJECT PLAN TO ADDRESS UNDER PERFORMANCE MANAGEMENT AREA TO POPULATE
MANAGEMENT AREA | CORRECTIONAL CENTRE | ACTIVITY / ACTIVITIES | RESPONSIBILITY | TIME FRAME | PROGRESS
Ncome | All Correctional Centres | Formulate VOD Forums in each centre Develop a tracing unit within the management area Encourage offenders to participate in VOD | Area Commissioner and Area Coordinator Corrections | October 2020 and ongoing | Formulate d VOD Forums in each centre Developed a tracing unit within the management area Encouraged offenders to participate in VOD
Pietermaritzburg | All Correctional Centres | Formulate VOD Forums in each centre Develop a tracing unit within the management area Encourage offenders to participate in VOD | Area Commissioner and Area Coordinator Corrections | October 2020 and ongoing | Formulate d VOD Forums in each centre Developed a tracing unit within the management area Encouraged offenders to participate in VOD
Waterval | All Correctional Centres | Formulate VOD Forums in each centre Develop a tracing unit within the management area Encourage offenders to participate in VOD | Area Commissioner and Area Coordinator Corrections | October 2020 and ongoing | Formulate d VOD Forums in each centre Developed a tracing unit within the management area Encouraged offenders to participate in VOD
PLAN TO ADDRESS UNDER PERFORMANCE:
Percentage increase of offenders, parolees and probationers participating in Restorative Justice Programme

## Slide 48
Thank You
THANK YOU
STRIVING FOR A SOUTH AFRICA IN WHICH PEOPLE ARE AND FEEL SAFE