## Slide 1
QUARTERLY REVIEW SESSION
Progress on the Implementation of Audit Action Plans
Quarter 2
2020/21 FY

## Slide 2
TABLE OF CONTENTS
Purpose and Background
Summary Report: Progress Made to Implement Audit Action Plans
Measures Undertaken to Improve Areas of Audit Qualifications

## Slide 3
PURPOSE AND BACKGROUND
1.1. Purpose
To report progress made to implement audit actions on findings as reported by the AGSA during 2019/20 financial year.
1.2. Background
AGSA reported a total of two hundred and four (204) findings during the 2018/19 financial year. The findings relates to audit conducted at Head Office, Kwa-Zulu Natal, Limpopo-Mpumalanga-North West, Western Cape and Gauteng regions.
These findings are as reported on the Final Management Letter and the Audit Report as communicated to the department on 23 July 2019 and 1 August 2019 respectively.

## Slide 4
2. SUMMARY REPORT: PROGRESS MADE TO IMPLEMENT AUDIT ACTION PLANS
In relation to the implementation of the 2018/19 financial year, the department has implemented 70%(142/204) of the findings raised and 30% (62//204) of the findings are in progress. The findings reported as in progress relates to instances were management have implemented some of the audit action plan activities per the Tracking Register however these activities are only considered as implemented when all activities, without exception, have been finalized.
In addition, the AGSA issued an Interim Management Report for 2019/20 financial year comprising indicating a total of one hundred and five (105) findings on regularity audit. These findings are normally dealt with or cleared during the final audit process and any outstanding matters/findings are incorporated into the final audit report and followed up from the time of finalization of the audit report.

## Slide 5
2. SUMMARY REPORT: PROGRESS MADE TO IMPLEMENT AUDIT ACTION PLANS - CONTINUED
Component/Region | Total Findings | Status of Implementation |  |  | Findings By Category |  | 
 |  | Not implemented | In progress | Implemented | Financial | Compliance | AOPO
Financial Accounting | 16 | 0 | 4 | 12 | 16 | 0 | 0
Procurement | 10 | 0 | 4 | 6 | 0 | 10 | 0
Logistics | 6 | 0 | 3 | 3 | 6 | 0 | 0
Contract Management | 14 | 0 | 5 | 9 | 12 | 2 | 0
Human Resource | 12 | 0 | 3 | 9 | 0 | 12 | 0
Internal Audit | 1 | 0 | 0 | 1 | 0 | 1 | 0
Social Reintegration | 3 | 0 | 0 | 3 | 0 | 0 | 3
Facilities Management | 5 | 0 | 4 | 1 | 0 | 0 | 5
GITO | 13 | 0 | 13 | 0 | 0 | 13 | 0
Legal Services | 3 | 0 | 0 | 3 | 3 | 0 | 0
Inspectorate | 5 | 0 | 5 | 0 | 0 | 5 | 0
Gauteng region | 13 | 0 | 2 | 11 | 2 | 7 | 4
KZN region | 46 | 0 | 4 | 42 | 13 | 27 | 6
LMN region | 30 | 0 | 3 | 27 | 9 | 18 | 3
WC region | 27 | 0 | 12 | 15 | 4 | 20 | 3
Total | 204 | 0 | 62 | 142 | 65 | 115 | 24
% of total | 100 | 0.0 | 30.4 | 69.6 | 31.9 | 56.4 | 11.8

## Slide 6: 3. MEASURES UNDERTAKEN TO IMPROVE AREAS OD AUDIT QUALIFICATIONS
Issued circulars and directives to guide management and staff on operational issues to be maintained to address audit outcomes. The department engaged the National Treasury to communicate challenges relating to implementation of Modified Cash Standards (MCS) as it relates to disclosure of Commitments This engagement resulted in positive outcomes as the National Treasury has amended the disclosure requirements for commitments (chapter 14) on the Annual Financial Statements. This amendment has in essence removed requirements to disclose commitments relating to goods and services, which had been a challenge for the department. Departments are only required to disclose capital commitments, which has not been a challenge in the past.

## Slide 7: 3. MEASURES UNDERTAKEN TO IMPROVE AREAS OF AUDIT QUALIFICATIONS - CONTINUED
In relation to Bed Space qualification as reported in 2018/19 financial year, all the G309s of the two hundred and forty one (241) centres have been captured. The department is undertaking the final stages of verification to eliminate all discrepancies between the ADS reports, the G309s and the actual physical bed space at centers.
In respect of Irregular Expenditure, the department finalized the process of reviewing the entire population of payments from 01 April 2019 to 31 March 2020 to ensure completeness of disclosure in the Annual Financial Statements. Additional irregular expenditure was identified and disclosed on the Irregular Expenditure Registers and disclosed on the note to the Annual Financial Statements.