## Slide 1
2020 ANNUAL STRATEGIC PLANNING SESSION
OMF PHASE II
WORKSTREAM 4

## Slide 2: Presentation outline
--
Purpose
Legislative framework
Public Service Operations Management Framework
DCS Value Chain
Composition of Work Streams & sub-work streams
Progress Workstream deliverables
Planned deliverables and timeframes
Conclusion
Notes: <number>

## Slide 3: Purpose
The purpose of the presentation is to:
Provide context to the DCS Operations Management Framework Phase II with a focus on the deliverables of Workstream 4: Change Management, and support to other workstreams in Phase Two
Provide a summary of the guiding prescripts, guidelines, policy mandates that inform the work to be delivered by Workstream 4: Change Management
Indicate the core members of Workstream 4: Change Management that have been appointed to deliver on Phase II
Provide progress of the work completed by Workstream 4: Change Management since the appointment of the workstream leaders and members in February 2019
Indicate the outstanding deliverables for Workstream 4: Change Management with timeframes against the OMF Phase II Charter
Provide concluding remarks on the deliverables of Workstream 4: Change Management and the movement into the next phase
Insert the title of your subtitle Here
Notes: <number>

## Slide 4: Legislative framework - Workstream 4
Flowing from the DCS Service Delivery Model (SDM) is the requirement to re-examine the department’s organisational design, as well as strengthening and amending governance frameworks and documents to ensure alignment to the SDM:
  MTSF 2019-2024: Outcome 3 – Education, skills and health
  NDP 2030 – Chapter 12: Building Safer Communities
  DCS Strategic Plan 2020 – 2025
  Tied to this SDM process is the adoption of a clear implementation framework, and change management plan, which recommends a staged implementation to enable organizational re-alignment
  Change Management Workstream to provide support to other workstreams in Operations Design Phase
  Implementation of the change management plan must be accompanied by dedicated resources to drive sustained change management

## Slide 5: DCS Operations Management Framework

## Slide 6: DCS Value Chain and Structure

## Slide 7: Phase II Workstreams
.
Workstream 1: People and structure alignment
Review the organisational structure
Conduct specialised HR exercises to define key concepts such as the ‘ideal correctional official’, the ideal culture, the competency sets required across the organisation for greater professionalisation
Deploy culture interventions
Workstream 2: Process and technology
Mapping of business processes reflective of the Service Delivery Model
Incorporating workflows into standardised documentation
Input of workflows into system design and enhancement
Training for users on processes and technology
Facilitate centralisation of ICT
Workstream 3: Governance
Update any affected policies
Update of the Delegations of Authority
Update the B-Order and ORP
Workstream 4: Change Management Implementation Plan
Set-up PMO and relevant governance structures (Project Management Office)
Define Change Management across Workstreams
Facilitate Change through the Design Phase
Change Readiness Assessment
Tailored Change Management Intervention and Communications
Workstream 5:
Self sufficiency
Defining the value of self sufficiency in support of self sustenance and revenue generation
Production workshops
Financial sustainability

## Slide 8: Composition of Workstream 4
Workstream 4
Change Management
Regional Comm
Coordinator KZN
Workstream Leader
DC Communications
Regional Comm
Coordinator WC
Regional Comm
Coordinator FS/NC
Regional Comm
Coordinator LMN
Regional Comm
Coordinator GP
Director Marketing and Promotions
Dir Internal Comm & Media Production
Dir Public Education, Stakeholder Relations and Media Services
Regional Comm Coordinator EC

## Slide 9: Overview of Workstream 4 progress
Communication and Engagement
50%
Selection and Capacitation of Change Leaders and Change Champions
40%
Monitoring and Evaluation
10%

## Slide 10: Effective change management is composed of frequent and clear communication, stakeholder engagement and transition and efforts that reinforce change…
Change Management and Communications
Frequent Communication
Engagement and Utilisation of Inputs

## Slide 11: …with clear strategic, leadership and operational alignment..
PMO
Project Owners
Management
Change Champion
Communications
Steering Committee
Ensure the buy-in and support from the top of the Organisation
Management Forum
Obtain sponsorship across the organisation through Change Champions and the Management Forums / Steering Committees
Extended Change Network
Utilise Change Champions to drive implementation operationally
Steering Committee
Ensure the buy-in and support from the top of the Organisation
Management Forum
Obtain sponsorship across the organisation through Change Champions and the Management Forums / Steering Committees
Extended Change Network
Utilise Change Champions to drive implementation operationally
Change Leaders/ Sponsors
For the change management to be successful, first gain engagement of Senior Leaders of DCS as Change Sponsors / Leaders
NC, CDCs & RC’s
Leadership involvement in the change process is critical as change should begin at the top

## Slide 12: …and a more comprehensive, hands-on approach is required
Change Management Objectives
Communication Plan
Change Readiness Assessment
Leadership and Management Support
Training & Capacity Building
Coaching and Support
Change Management Tools
The size of the organisation and many bureaucratic layers blur the transparency of decisions being made at the top level
Communication and understanding is critical to the success of this process
The current organisational culture has a multitude of paradoxical spectrums that require facilitation towards a clearly defined culture
There are many long-serving employees set in their ways
This makes acceptance of new models and collaboration difficult
Performance management through SLAs will create tension and anxiety, however, this can be used to drive performance in the organisation
Regular and Sustained Communication
Share Successes & Build Momentum
Regular Availability for Q&A
Transparency and Fairness
Organisational Culture
Collaboration and Performance Management
Change that is owned and driven by DCS would allow for greater and quicker organisational adoption

## Slide 13: Detailed progress on Workstream 4:
DELIVERABLES | ACTIVITIES | PROGRESS TO DATE | COMMENT
Phase 2: During Design and Development stages, focus should be on developing broad consensus and understanding through consultations and engagement | For the short-medium term, the design phase of workstreams (Phase II), the SDM proposes the following Communications Framework and Plan: One-on-one meetings Roadshows Workshops Departmental/Staff meetings Email Website/Intranet Newsletters Notice Boards/Pamphlets/Banners/Branding | Prior to Kopanong 2018, Branches and Regions were requested to identify key issues Environmental analysis was conducted with a sample of officials at salary level 11 to 12 in the form of workshop, and SMS through a survey questionnaire Pre, actual and post communication activities for DCS 2018 Kopanong Strategic Planning session, which included customized branding, content and various communication products | Strategic methods to facilitate broad understanding and gain group consensus Information and general communication through periodic communiques Engagement through one-on-one departmental interviews, process reviews, etc. Involvement through defining and designing micro-structures, etc.

## Slide 14: Detailed progress on Workstream 4:
DELIVERABLES | ACTIVITIES | PROGRESS TO DATE | COMMENT
Phase 2 (Cont.) | Utilisation of critical functions or individuals required for change: One-on-one meetings; Roadshows | Handover of 2018 Kopanong Strategic Planning Report, 12 October 2018 Roadshows on the outcomes of the Kopanong Strategic Planning Session 2018 Various Workstreams sessions/engagements 2019 Strategic Planning Session Ministerial Engagements Deputy Minister’s visits National Commissioner’s/COC’s visits | A balanced approach, utilising various communication methods is required which includes written, one-on-one and group communication All elements together were used to drive change

## Slide 15: Detailed progress on Workstream 4:
DELIVERABLES | ACTIVITIES | PROGRESS TO DATE | COMMENT
Phase 2 (Cont.) | Strategic methods to facilitate broad understanding and gain group consensus: Workshops; Departmental/Staff meetings | Various Branch, Regional and Management Area Engagements Since 2018, numerous communication support to the various workstreams and OMF processes as part of fostering change (e.g.) Insourcing of kitchens HCCs Workshops Covid-19 Response Strategy DMRT Meetings NOC, MOC, LOC | This was done to: Create anticipation by kicking-off implementation with multi-pronged communications, including emails, roadshows, pamphlets and notices Follow-up and sustain through regular touch-points, including departmental meetings, newsletters and email

## Slide 16: Detailed progress on Workstream 4
DELIVERABLES | ACTIVITIES | PROGRESS TO DATE | COMMENT
Phase 2 (Cont.) | Regular communication methods that seek to inform staff on changes, progress and successes: Email; Website/Intranet; Newsletters; Notice Boards/Pamphlets/Banners/Branding | DCS Governance Committees Manual: Premanco, Manco, Strategic Operations Management Committee Centre-centric posture: Centre of Excellence, Theatres of Operation Business Process Management Virtual meetings 2020 Strategic Planning | Maintain clarity of purpose, transparency, fairness and objectives in communications including the management of staff expectations

## Slide 17: Detailed progress on Workstream 4
DELIVERABLES | ACTIVITIES | PROGRESS TO DATE | COMMENT
Define Change Management Across Workstreams | Set up change management workstreams with defined objectives and clear approach to change management Enable the setup of change teams across DCS Design Change Readiness Assessment framework and determine measures of change readiness | Next Phase/s | 

## Slide 18: Detailed progress on Workstream 4
DELIVERABLES | ACTIVITIES | PROGRESS TO DATE | COMMENT
Facilitate Change through the Design Phase | Within each workstream, facilitate change through frequent communication and stakeholder engagement. Stakeholder engagement is vital for inputs into the process, buy-in of key role-players and overall shaping and adoption of the intervention output Implementation of Communications Framework and Plan – 6th Administration Building of Organisational Support | Next Phase/s 1 April 2021 Presentations done at RMC’s and NATMANCO | 

## Slide 19: Detailed progress on Workstream 4
DELIVERABLES | ACTIVITIES | PROGRESS TO DATE | COMMENT
Change Readiness Assessment | Conduct change readiness assessments to guide the requirements for the change management intervention. Areas the assessment could measure include communication, roles and responsibilities, leadership alignment, internal change network, resourcing, enablement, project health, embedding of the change. | Next Phase/s | 

## Slide 20: Detailed progress on Workstream 4
DELIVERABLES | ACTIVITIES | PROGRESS TO DATE | COMMENT
Tailored Change Management Intervention and Communications Monitoring and Evaluation of Change Process Sustain Change in DCS | Based on the findings of the assessment, tailored intervention must target weak areas and reinforce strength areas (e.g.) the intervention could target a weak area of leadership alignment through greater leadership communication of a single, consistent message | Next Phase/s | 

## Slide 21: Remaining deliverables and timeframes
MONTH 1
Week 1
Week 2
Week 3
Week 4
Not set up as yet
Deliverable 1
Set up PMO and relevant governance structures
2018 – Ongoing
xx
Deliverable 2
Implementation of Communications Framework & Plan
Next Phase/s
Deliverable 5
Change Readiness Assessment
Next Phase/s
xx
Deliverable 3
Define Change Management across Workstreams
Deliverable 4
Facilitate Change through the Design Phase
Next Phase/s
MONTH 2
Week 1
Week 2
Week 3
Week 4
MONTH 3
Week 1
Week 2
Week 3
Week 4
Deliverable 6
Tailored Change Management Intervention & Communications
Next Phase/s
xxx

## Slide 22: Risk Management
Deliverable | Strategic Risk | Risk Mitigation
Change Management Implementation Plan | Resistance to change | Intensify awareness at various levels in the organisation Enhance stakeholder engagement

## Slide 23: Conclusion
The Strategic Planning Roadshows were well received by officials
Human Resources issues dominated discussions at all sessions. Most concerns related to staff shortages at centre level, review of the current shift system, centre/non-centre based policy, review of the organizational structure and post establishment, shortage of uniform as well as absence of promotion and retention policy
A great deal of attention was given to training and development. This is suggestive of a positive attitude of staff to change and embrace the future of corrections. Management should consider suggestions by officials to strengthen the current training curriculum and provide specialized training for different types of work/fields in corrections
There is an overwhelming positive response to the new strategic direction of the Department, and the bottom-up approach adopted. This positive attitude is also reflected in the responses to the evaluation questionnaire completed by participants at the end of the roadshows
The main concern raised by officials was a monitoring and evaluation mechanism for the new strategic direction of DCS. Staff expressed fear that the new strategic direction of the Department may not be fully realized for various reasons, including change in leadership
Change Management serves two core purposes: To facilitate the process of change, and reinforce change

## Slide 24: Conclusion
Within a large organisation such as DCS, change management becomes critical and must be effectively managed
Cannot afford to adopt a trial and error, ad-hoc, approach, as this may cause irreparable harm
As per Service Delivery Model (SDM), implementation of the change management plan must be accompanied by dedicated resources to drive sustained change management
SDM: Setting-up PMO and relevant governance structures (Project Management Office) is imperative
PMO responsible for Strategic Implementation and Change Management Support: provide technical expertise to solving key workstream or activity challenges; management of complexity that arises from migration; management of the change management process including communication protocols; ensuring transparency and compliance; key function of the PMO is monitoring and evaluation of the workstreams towards implementing the SDM
As part of the next phase/s, change management focus shifts towards Training, Coaching and Support and Reinforcement
Integral facets of Change Management include Coaching and Support, Leadership and Management Support as well as Training and Capacity Building

## Slide 25: Conclusion
South Africa’s future rests with its people. As DCS, may we continue to both understand and appreciate the great responsibility we have been tasked with; to help, to serve and to lead. We dare not let our country, and our people, down
Change is the law of life. And those who look only to the past or present are certain to miss the future (John F. Kennedy)
There is no better time than right now!

## Slide 26
Questions?

## Slide 27: Thank you!
Notes: <number>