## Slide 1: Presentation on DCS 2nd Quarter Actual Performance Report (2016/2017) November 2016
PRESENTATION ON Q4 PERFORMANCE
BRANCH: COMMUNITY CORRECTIONS
17 May 2021

## Slide 2
2020/21
PERFORMANCE TARGETS NOT ACHIEVED
2020/21
QUARTER 4

## Slide 3
PROGRAMME 5
Social Reintegration

## Slide 4
PROGRAMME 5: SOCIAL REINTEGRATION SUB PROGRAMME: COMMUNITY REINTEGRATION |  |  |  |  |  |  | 
Key Performance Indicators | Q4 Target 2020/21 | Quarter 4 Performance | Reasons for under achievement | Corrective action | Timelines | Responsibility | Progress on the implementation of corrective action
'Percentage increase of victims participating in Restorative Justice Programme | 7% | 3,34% (11 833/24 815) | Due to COVID 19 restrictions gatherings were profited or limited to a small number, as result the performance of the program was negatively affected. | Use of other mechanisms like audio visual and written presentation from both victims and offenders. When levels of lockdown is eased/ amended then more number of participants increased to more bigger venues. | When the need requires to do so within the prescripts of COVID 19 Regulations | CommCorr Branch | The numbers increased at the last quarter compared to the 1st and 2nd quarters.
Percentage increase of offenders, parolees and probationers participating in Restorative Justice Programme | 3% | 1,48% (3 791/7 691) | Due to COVID 19 restrictions gatherings were profited or limited to a small number, as result the performance of the program was negatively affected. | Use of other mechanisms like audio visual and written presentation from both victims and offenders. When levels of lockdown is eased/ amended then more number of participants increased to more bigger venues. | When the need requires to do so within the prescripts of COVID 19 Regulations | CommCorr Branch | The numbers increased at the last quarter compared to the 1st and 2nd quarters.
INDICATORS NOT ACHIEVED DURING 2020/21 – Q4

## Slide 5
SOURCE OF UNDER-ACHIEVEMENT AT REGIONAL LEVEL
'Percentage increase of victims participating in Restorative Justice Programme
Q4 TARGET 2020/21 | QUARTER 4 PERFORMANCE | REGION THAT CONTRIBUTED TOWARDS UNDER-ACHIEVEMENT | REASONS FOR UNDER PERFORMANCE | ROOT CAUSES | ASSOCIATED RISKS
LMN > (7%) | (4 740/4 7932) 6,92% |  | 'The Region embarked on an aggressive drive after the upliftment of Alert Level 3 to Alert level 1 in ensuring the achievement of the set target | COVID 19 Regulations on lockdown | 
FS/NC > (7%) | (1 773/6 980) 1,78% |  | 'Target not achieved , COVID 19 Regulations restricted movements to trace victims | COVID 19 Regulations on lockdown | 
KZN > (7%) | (2 439/3 575) 4,78% |  | 'Target not achieved , COVID 19 Regulations restricted movements to trace victims | COVID 19 Regulations on lockdown | 
W.C > (7%) | (642/2 162) 2,08% |  | 'Restriction brought about by DMR seriously curtailed the rendering of restorative justice programmes. If target is to be achieved more VOD facilitators and SAWs must be appointed to assist with victim tracing and facilitation of restorative justice programmes to deal with the backlog. | 'Restriction brought about by DMR seriously curtailed the rendering of restorative justice programmes. If target is to be achieved more VOD facilitators and SAWs must be appointed to assist with victim tracing and facilitation of restorative justice programmes to deal with the backlog. | 
GP > (7%) | (1 257/4 200) 2,10% |  | 'Non availability of victims due to COVID-19 restrictions. | COVID 19 Regulations on lockdown | 
E.C > (7%) | (9 82/3 106) 2,21% |  | 'Target not achieved , COVID 19 Regulations restricted movements to trace victims | COVID 19 Regulations on lockdown | 

## Slide 6
SOURCE OF UNDER-ACHIEVEMENT AT REGIONAL LEVEL Percentage increase of offenders, parolees and probationers participating in Restorative Justice Programme
Q4 TARGET 2020/21 | QUARTER 4 PERFORMANCE | REGION THAT CONTRIBUTED TOWARDS UNDER-ACHIEVEMENT | REASONS FOR UNDER PERFORMANCE | ROOT CAUSES | ASSOCIATED RISKS
LMN > (3%) | (1 585/1 574) 3,02% |  | 'The Region embarked on an aggressive drive after the upliftment of Alert Level 3 to Alert level 1 in ensuring the achievement of the set target | 'The Region embarked on an aggressive drive after the upliftment of Alert Level 3 to Alert level 1 in ensuring the achievement of the set target | 
FS/NC > (3%) | (422/1 650) 0,77% |  | 'Target not achieved , COVID 19 Regulations restricted movements to trace victims | COVID 19 Regulations on lockdown | 
KZN > (3%) | (451/838) 1,61% |  | 'Target not achieved , COVID 19 Regulations restricted movements to trace victims | COVID 19 Regulations on lockdown | 
W.C > (3%) | (291/1 042) 0,84% |  | 'Restriction brought about by DMR seriously curtailed the rendering of restorative justice programmes. If target is to be achieved more VOD facilitators and SAWs must be appointed to assist with victim tracing and facilitation of restorative justice programmes to deal with the backlog. | COVID 19 Regulations on lockdown shortage of SAW to do tracing and facilitation of the programme | 
GP > (3%) | (554/1 303) 1,28% |  | 'Non availability of victims due to COVID-19 restrictions. | COVID 19 Regulations on lockdown | 
E.C > (3%) | (488/1 284) 1,14% |  | 'Target not achieved , COVID 19 Regulations restricted movements to trace victims | COVID 19 Regulations on lockdown | 

## Slide 7
Thank You
THANK YOU
STRIVING FOR A SOUTH AFRICA IN WHICH PEOPLE ARE AND FEEL SAFE